# Phase 0 (Spike) — Work Breakdown: phases → tasks → subtasks

# Phase 0 (Spike) — Work Breakdown: phases → tasks → subtasks

Revision: 2 Last modified: 2026-07-04T12:00:00Z Rev 2: Independent gap-analysis pass (§14 risk register now cross-references v00-meta/decision-register.md's per-decision reversal criteria so a gate failure's architectural consequence is traceable to the exact decision it re-opens, not just a prose fallback). No contradictions found against HelixVPN-Phase0-Spike.md (the original CLD source) or v07-execution/{workable-items-model,dependency-graph, subtask-deepening-p1}.md — this WBS's 3-tier epic→task→subtask breakdown, gate evidence methodology (§12), and risk register (§14) were independently verified already concrete (falsifiable acceptance + captured-evidence method per item); R5 (task/subtask tier asymmetry, REFINEMENT_NOTES.md) does not apply to this document — Phase 0 was always the 3-tier side of the asymmetry.

Master technical specification — document 06 of the HelixVPN set. Scope: the complete Work Breakdown Structure (WBS) for Phase 0 — the Spike: every exit gate G1..G6 (question + go/no-go bar), every milestone S0..S8 decomposed into numbered TASKS and SUBTASKS with stable DB-ready ids HVPN-P0-NNN, and the surviving interfaces / harnesses (iOS memory rig, Go-vs-Rust edge benchmark, netns + nftables-DPI + netem rig with concrete commands). This is a SPEC — it describes the work and its interfaces; it does NOT build the product (2–3 refinement passes follow). This document is the single source for the workable-items SQLite DB (§11.4.93/.95): the HVPN-P0-NNN rows + fields below are authored to load directly.

Source evidence cited inline by id: [04_P0] = 04_VPN_CLD/HelixVPN-Phase0-Spike.md; [04_ARCH] = 04_VPN_CLD/HelixVPN-Architecture-Refined.md; [04_P1] = Phase1-MVP; [SYNTHESIS]; LLM analyses [02_QWN] [01_DSK] [07_GMI] [10_KMI] [11_MST]; external facts [research-masque] (RFC 9297/9298/9221), [research-boringtun], [research-quinn].

## 0. How to read this WBS (and the DB schema it populates)

Phase 0 is time-boxed to ~3–4 focused weeks [04_P0 §0]. It produces throwaway-quality implementations behind production-quality interfaces: the traits, FFI signatures, and wire contracts here are meant to survive into Phase 1 [04_P0 intro]. A gate that cannot be cleared inside the box is the finding — escalate the decision rather than overrun silently [04_P0 §0, §13].

### 0.1 Decomposition hierarchy

PHASE 0 (Spike)
 ├── EXIT GATES        G1..G6              — the go/no-go questions (§1)
 ├── MILESTONES        S0..S8              — independently demoable slices (§3..§11)
 │     ├── TASKS       HVPN-P0-NNN         — a unit of delivery (own acceptance + evidence)
 │     │     └── SUBTASKS HVPN-P0-NNN      — the smallest tracked work, each its own row
 └── CROSS-CUTTING     HVPN-P0-077..080    — harness, decision log, DB/CI, infra (§12)

Every TASK and every SUBTASK is a workable item with the same closed field set, so the table rows below load 1:1 into the docs/workable_items.db schema (§0.3). IDs are monotonic, never renumbered (§11.4.54): allocated once, parent expresses hierarchy.

### 0.2 Field dictionary (every item row carries these)

| Field | Meaning |
| --- | --- |
| id | stable HVPN-P0-NNN (§11.4.54) — primary key, never reused |
| parent | the owning milestone id (S0..S8) or task id; — for milestone-level tasks |
| kind | task ¦ subtask ¦ gate |
| title | ≥6-word self-contained meaning (§11.4.91) |
| gate | which exit gate(s) this item advances: G1..G6 or — |
| description | what / how it manifests / acceptance intent (§11.4.148 D2) |
| depends_on | upstream HVPN-P0-NNN ids that MUST be done first |
| deliverable | the concrete artifact produced (file/binary/CSV/report) |
| acceptance | falsifiable pass condition with captured PHYSICAL evidence (§11.4.5/.69/.107) |
| est_effort | engineer-days (rough, [04_P0 §2] day estimates are the anchor) |
| test_types | the §11.4.169 closed-set test-type codes required (§0.4) |

### 0.3 Workable-items DDL (§11.4.93 — this WBS loads into it)

-- docs/workable_items.db  (git-tracked, §11.4.95). Phase-0 subset of the canonical schema.
CREATE TABLE IF NOT EXISTS items (
    id            TEXT PRIMARY KEY,                       -- 'HVPN-P0-001'
    parent        TEXT REFERENCES items(id),              -- milestone/task ownership
    kind          TEXT NOT NULL CHECK (kind IN ('task','subtask','gate','milestone')),
    type          TEXT NOT NULL CHECK (type IN ('Bug','Feature','Task')) DEFAULT 'Task',
    status        TEXT NOT NULL DEFAULT 'Queued',         -- §11.4.15 closed set
    severity      TEXT NOT NULL DEFAULT 'Normal',
    title         TEXT NOT NULL CHECK (length(title) >= 40),   -- §11.4.91
    gate          TEXT,                                   -- 'G1'..'G6' or NULL
    description   TEXT NOT NULL CHECK (length(description) >= 40),
    depends_on    TEXT NOT NULL DEFAULT '[]',             -- JSON array of ids
    deliverable   TEXT NOT NULL,
    acceptance    TEXT NOT NULL,
    est_effort_d  REAL NOT NULL DEFAULT 1.0,
    test_types    TEXT NOT NULL DEFAULT '[]',             -- JSON array of §11.4.169 codes
    created_at    TEXT NOT NULL,
    modified_at   TEXT NOT NULL
);
CREATE TABLE IF NOT EXISTS gates (
    id            TEXT PRIMARY KEY,                       -- 'G1'..'G6'
    question      TEXT NOT NULL,
    go_no_go_bar  TEXT NOT NULL,
    section       TEXT NOT NULL,
    outcome       TEXT NOT NULL DEFAULT 'pending'
                  CHECK (outcome IN ('pending','pass','fail','rust','go')),
    evidence_path TEXT                                    -- §11.4.5 captured evidence
);
CREATE INDEX IF NOT EXISTS idx_items_parent ON items(parent);
CREATE INDEX IF NOT EXISTS idx_items_gate   ON items(gate);

### 0.4 §11.4.169 test-type code map (used in the test_types column)

| Code | §11.4.169 test type | Phase-0 instantiation |
| --- | --- | --- |
| UT | unit | Rust #[cfg(test)], Dart test, Go _test.go |
| IT | integration (real System, infra via containers submodule §11.4.76) | netns rig + edge + connector, booted on-demand |
| E2E | end-to-end | client overlay namespace → curl http://10.10.0.20/ |
| FA | full-automation (§11.4.25/.52/.98, deterministic §11.4.50) | make spike one-shot, N=3 identical runs |
| CH | Challenges (challenges submodule §11.4.27(B)) | per-gate Challenge scoring on captured evidence |
| HQA | HelixQA (helix_qa submodule) | autonomous QA session against the slice |
| LOAD | DDoS / load-flood | 1/10/100 concurrent iperf3 + handshake-flood |
| SEC | security (§11.4.10 + security submodule) | DPI evasion, wire fingerprint, no-plaintext-leak |
| SC | stress + chaos (§11.4.85) | iface flap, packet loss, process kill mid-transfer |
| CONC | concurrency / atomicity | three-loop orchestrator under concurrent send/recv |
| RACE | race-condition / deadlock | cargo test --features loom, -race on Go edge |
| MEM | memory | RSS sampling — iOS Instruments / /proc / dumpsys |
| BENCH | benchmarking / performance | bench.sh throughput / CPU-per-Gbps / p99 CSV |

Per §11.4.169, the ONLY permitted absence of a warranted type is an honest §11.4.3 SKIP-with-reason (e.g. iOS MEM on a machine with no device → topology_unsupported), never a silent gap. Four-layer enforcement per §11.4.4(b) applies to every TASK closure.

## 1. Exit gates G1..G6 (the questions Phase 0 must answer)

A "no-go" on G3 or G4 changes the architecture, not just the schedule — that is exactly why they are in Phase 0 [04_P0 §0]. Gates load into the gates table (§0.3).

| Gate | Question | Go / No-go bar | Section | Decides |
| --- | --- | --- | --- | --- |
| G1 | Can helix-core (Rust + boringtun) move real traffic client→gateway→connector LAN over plain UDP? | iperf3 through-tunnel ≥ 80% of bare-link throughput; ping/curl to 10.10.0.20:80 succeeds | §3–§5, §12 | core viability |
| G2 | Can the same core do it over MASQUE/QUIC (WG-in-HTTP/3)? | Works through a DPI-style UDP block on :51820; ≥ 50% of plain-UDP throughput; survives 5% loss better than a UDP-over-TCP strawman; flow classified HTTP/3 with no WG signature | §6, §12 | obfuscation D1 [SYNTHESIS] |
| G3 | Does the Rust core run inside an iOS NEPacketTunnelProvider under its memory ceiling with headroom? | Extension-process steady-state RSS under the device-enforced ceiling with ≥ 30% headroom across a 30-min, 1 GB transfer, for both plain-UDP and MASQUE | §10 | make-or-break Rust-on-every-platform thesis (D2) |
| G4 | Go vs Rust for the gateway edge — which terminates MASQUE better, all-in? | Decision recorded with benchmark numbers (CPU/Gbps, p99, churn, memory) + reuse/velocity assessment | §7, §12, §13 | edge language D5 |
| G5 | Is the flutter_rust_bridge FFI boundary clean enough to drive the core from Dart? | Flutter-Linux app toggles the tunnel and shows live status (Connecting→Handshaking→Connected{transport,rtt}) driven only by the core's event stream | §8 | FFI boundary |
| G6 | Does push-based reconciliation work at all (static map → core brings up peers)? | Core consumes a map.json delta and converges without restart; the newly-advertised network becomes reachable | §11 | push model seed |

INSERT INTO gates (id,question,go_no_go_bar,section,outcome) VALUES
 ('G1','plain-UDP slice client→gw→connector LAN','iperf3 ≥80% bare link; curl 10.10.0.20:80 OK','§3-§5','pending'),
 ('G2','same core over MASQUE/QUIC through DPI block','≥50% of plain-UDP; survives 5% loss > UoT; classified HTTP/3','§6','pending'),
 ('G3','Rust core in iOS NEPacketTunnelProvider memory','steady RSS < ceiling with ≥30% headroom, both transports, 30-min 1GB','§10','pending'),
 ('G4','Go vs Rust gateway edge for MASQUE','decision recorded with CPU/Gbps, p99, churn, mem + velocity','§7','pending'),
 ('G5','flutter_rust_bridge FFI drives core from Dart','Flutter-Linux toggle + live status from event stream','§8','pending'),
 ('G6','push-based reconcile from static map','map delta → converge, no restart, network reachable','§11','pending');

## 2. Milestone map (dependency graph + schedule)

S3, S4, S7 are the high-risk milestones; sequence so a failure surfaces early. S0–S2 are the foundation everything else stands on [04_P0 §2].

Parallelism note (§11.4.103/.94): S5/S6/S8 do not depend on S3/S4 and run as background streams concurrently with the high-risk critical path; S4 and S7 must not share the single benchmark host at once (§11.4.119 single-resource-owner — the bench rig is an exclusive resource; partition device ownership).

## 3. Milestone S0 — Cargo workspace + Transport trait + plain-UDP (HVPN-P0-001..010)

Proves: the abstraction compiles and round-trips. Effort: ~2d. Gate: foundation for G1. Demo: loopback echo test green.

### TASK HVPN-P0-001 — Bootstrap the helix-core Cargo workspace skeleton

| Field | Value |
| --- | --- |
| parent | S0 |
| kind | task · type Task |
| title | Bootstrap helix-core Cargo workspace with the six surviving crates |
| gate | — (foundation for G1/G5) |
| description | Create the [workspace] with crates/{helix-transport,helix-wg,helix-tun,helix-core,helix-ffi} + bin/{helix-client,helix-connector} per [04_P0 §4.1]; pin Rust toolchain (rust-toolchain.toml, 1.82+); wire CI-less local check (cargo check --workspace) per §11.4.156. |
| depends_on | — |
| deliverable | helix-core/Cargo.toml + crate stubs that cargo check --workspace passes |
| acceptance | cargo check --workspace exit 0; cargo tree shows the 6-crate graph; captured terminal recording (§11.4.158) |
| est_effort | 0.5 |
| test_types | UT |

Surviving workspace layout (must match Phase 1 monorepo helix-core/ [04_ARCH §11]):

helix-core/
├── Cargo.toml                  # [workspace]
├── rust-toolchain.toml         # channel = "1.82.0"
├── crates/
│   ├── helix-transport/        # Transport trait + registry (shared client+edge+connector)
│   │   ├── src/lib.rs
│   │   ├── src/plain_udp.rs     # S0/S1
│   │   └── src/masque.rs        # S3
│   ├── helix-wg/               # boringtun wrapper
│   ├── helix-tun/              # OS tun abstraction (Linux now)
│   ├── helix-core/             # orchestrator: tun<->wg<->transport + event stream
│   └── helix-ffi/              # flutter_rust_bridge surface (S5)
└── bin/
    ├── helix-client.rs
    └── helix-connector.rs

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| Workspace manifest + 6 crate stubs | HVPN-P0-002 | Cargo.toml + lib.rs stubs | cargo check --workspace exit 0 | UT |
| Toolchain pin + dep baseline (tokio, bytes, async-trait, anyhow, tracing) | HVPN-P0-003 | rust-toolchain.toml, locked Cargo.lock | cargo build --workspace exit 0; lockfile committed | UT |

### TASK HVPN-P0-004 — Define the Transport trait + registry + dial() (THE survivor interface)

The single most important interface in the project [04_P0 §4.2]: one trait, three consumers, N transports. Everything obfuscation-related hides behind it. The transport NEVER sees plaintext (invariant I1, [01-data-plane §0.1]).

| Field | Value |
| --- | --- |
| parent | S0 |
| kind | task · type Feature |
| title | Define the surviving Transport trait, TransportConfig, and dial() registry |
| gate | — (underpins G1, G2, G4) |
| description | Author the byte-stable Transport trait carrying unreliable WG datagrams (I2) + TransportConfig enum + dial() factory that the auto-escalation ladder later drives. Interface MUST survive into Phase 1 unchanged. |
| depends_on | HVPN-P0-002 |
| deliverable | helix-transport/src/lib.rs with the trait + config + dial() |
| acceptance | trait object Box<dyn Transport> usable from client/connector/edge crates; doctests compile; §11.4.92 multi-pass review marker recorded |
| est_effort | 0.5 |
| test_types | UT, CONC |

// helix-transport/src/lib.rs — the survivor interface [04_P0 §4.2]
use async_trait::async_trait;
use bytes::Bytes;
use std::net::SocketAddr;

/// A bidirectional carrier for already-encrypted WireGuard datagrams.
/// The transport NEVER sees plaintext; it only changes how WG bytes look on the wire.
#[async_trait]
pub trait Transport: Send + Sync {
    async fn send(&self, datagram: Bytes) -> Result<(), TransportError>;   // one WG datagram out
    async fn recv(&self) -> Result<Bytes, TransportError>;                 // next WG datagram in (cancel-safe)
    fn kind(&self) -> &'static str;                                        // "plain-udp" | "masque-h3" | ...
    fn effective_mtu(&self) -> u16;                                        // WG MTU after transport overhead
}

#[derive(Clone, Debug)]
pub enum TransportConfig {
    PlainUdp { peer: SocketAddr, bind: SocketAddr },
    Masque   { url: String, sni: String, bind: SocketAddr },   // https://gw:443
    // Phase 1+: Shadowsocks { .. }, UdpOverTcp { .. }, Lwo { .. }
}

#[derive(thiserror::Error, Debug)]
pub enum TransportError {
    #[error("io: {0}")] Io(#[from] std::io::Error),
    #[error("handshake failed: {0}")] Handshake(String),
    #[error("closed")] Closed,
}

/// Build a transport from config. The escalation ladder (auto mode) just
/// constructs the next variant on repeated handshake failure.
pub async fn dial(cfg: TransportConfig) -> Result<Box<dyn Transport>, TransportError> { /* S1/S3 */ }

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| Trait + TransportError + effective_mtu contract | HVPN-P0-005 | lib.rs trait | cargo doc clean; trait object-safe | UT |
| TransportConfig enum + dial() factory skeleton | HVPN-P0-006 | dial() matching on config | returns Box<dyn Transport> for PlainUdp | UT |
| Transport registry + kind() label table (for metrics/logs) | HVPN-P0-007 | registry map kind→ctor | round-trips label; no per-flow durable state (I5) | UT, SEC |

### TASK HVPN-P0-008 — Plain-UDP transport + loopback echo (the throughput baseline)

| Field | Value |
| --- | --- |
| parent | S0 |
| kind | task · type Feature |
| title | Implement plain-UDP Transport and prove a loopback echo round-trip |
| gate | G1 (baseline that all transports are measured against) |
| description | Trivial PlainUdp over tokio::net::UdpSocket [04_P0 §4.3]; gives the baseline every other transport's ≥50% bar (G2) is computed against; loopback echo test validates the trait round-trips. |
| depends_on | HVPN-P0-006 |
| deliverable | helix-transport/src/plain_udp.rs + tests/loopback_echo.rs |
| acceptance | echo test sends 10k 1280-byte datagrams loopback, 0 lost, order-independent; captured CSV of round-trip count |
| est_effort | 0.5 |
| test_types | UT, IT, CONC, BENCH |

// helix-transport/src/plain_udp.rs
pub struct PlainUdp { sock: tokio::net::UdpSocket, peer: SocketAddr }
#[async_trait]
impl Transport for PlainUdp {
    async fn send(&self, dg: Bytes) -> Result<(), TransportError> { self.sock.send_to(&dg, self.peer).await?; Ok(()) }
    async fn recv(&self) -> Result<Bytes, TransportError> {
        let mut buf = vec![0u8; 1500];
        let n = self.sock.recv(&mut buf).await?; buf.truncate(n); Ok(Bytes::from(buf))
    }
    fn kind(&self) -> &'static str { "plain-udp" }
    fn effective_mtu(&self) -> u16 { 1420 }   // standard WG-over-IPv4
}

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| PlainUdp send/recv + MTU=1420 | HVPN-P0-009 | plain_udp.rs | loopback single datagram round-trips | UT, IT |
| Loopback echo soak (10k dg) + datagram-loss census | HVPN-P0-010 | tests/loopback_echo.rs + CSV | 0 lost @ loopback; deterministic over N=3 (§11.4.50) | IT, CONC, BENCH, FA |

## 4. Milestone S1 — helix-wg + helix-tun + orchestrator (HVPN-P0-011..021) · G1

Proves: WG core works through our transport — Linux client ↔ Linux gateway plain-UDP WG up; ping overlay IP. Effort: ~3d.

### TASK HVPN-P0-011 — helix-wg boringtun wrapper (handshake / encrypt / timers)

| Field | Value |
| --- | --- |
| parent | S1 |
| kind | task · type Feature |
| title | Wrap boringtun Tunn state machine into the helix-wg verdict API |
| gate | G1 |
| description | boringtun is the Phase-0 choice [04_P0 §4.4, research-boringtun]: pure-Rust userspace WG, no kernel module, identical on Linux/Android/iOS (the iOS path — no kernel WG on iOS). Wrap Tunn; pump its timer; route its four output verdicts into WgVerdict. |
| depends_on | HVPN-P0-003 |
| deliverable | helix-wg/src/lib.rs (WgPeer + WgVerdict) |
| acceptance | two WgPeers complete a Noise IK handshake in-process; data packet encrypts→decrypts to identical plaintext; captured test log |
| est_effort | 1.5 |
| test_types | UT, CONC, RACE, MEM |

// helix-wg/src/lib.rs (sketch) — survives into Phase 1 [04_P0 §4.4]
pub struct WgPeer { tunn: boringtun::noise::Tunn /* keys, endpoint */ }
pub enum WgVerdict { WriteToTransport(Bytes), WriteToTun(Bytes), Nothing, Err(WgError) }
impl WgPeer {
    pub fn handle_transport_in(&mut self, datagram: &[u8], scratch: &mut [u8]) -> WgVerdict { /* in: from transport */ }
    pub fn handle_tun_out(&mut self, ip_pkt: &[u8], scratch: &mut [u8]) -> WgVerdict { /* out: from TUN */ }
    pub fn tick(&mut self, scratch: &mut [u8]) -> WgVerdict { /* ~every 100-250ms: keepalive/rekey */ }
}

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| WgPeer::handle_transport_in / handle_tun_out | HVPN-P0-012 | encrypt/decrypt paths | in-process handshake + data round-trip | UT, CONC |
| tick() timer pump (keepalive/rekey) | HVPN-P0-013 | timer loop | rekey fires after rekey-after-time; no deadlock under loom | UT, RACE |
| Scratch-buffer allocation discipline (bounded, no per-packet alloc) | HVPN-P0-014 | reusable scratch | RSS flat across 1M packets (/proc sample) — feeds G3 | MEM, BENCH |

### TASK HVPN-P0-015 — helix-tun Linux TUN device abstraction

| Field | Value |
| --- | --- |
| parent | S1 |
| kind | task · type Feature |
| title | Provide the helix-tun Linux TUN device read/write abstraction |
| gate | G1 |
| description | OS TUN abstraction (Linux now; platform shims call in later via the same trait). Owns /dev/net/tun open, MTU/route config, async read/write of IP packets. On mobile the platform shim owns the TUN and feeds the same API [04_P0 §9 note]. |
| depends_on | HVPN-P0-003 |
| deliverable | helix-tun/src/lib.rs + Linux impl |
| acceptance | brings up helix0 iface, assigns overlay IP, echoes an injected IP packet back to the reader; captured ip addr + pcap |
| est_effort | 0.5 |
| test_types | UT, IT |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| TunDevice trait + Linux /dev/net/tun impl | HVPN-P0-016 | lib.rs + linux.rs | iface appears in ip link; read/write works | IT |
| MTU/route config + non-blocking async I/O | HVPN-P0-017 | config fns | MTU=1420 set; no busy-spin (CONC check) | UT, CONC |

### TASK HVPN-P0-018 — Orchestrator three-loop core + event stream + client/connector binaries

| Field | Value |
| --- | --- |
| parent | S1 |
| kind | task · type Feature |
| title | Build the orchestrator three-loop core, event stream, and dual-mode binaries |
| gate | G1 |
| description | The orchestrator runs three loops — tun→wg→transport, transport→wg→tun, timer tick [04_P0 §4.5] — and exposes a tokio::sync::broadcast event stream (Connecting¦Handshaking¦Connected{transport,rtt}¦Reconnecting¦Down{reason}) that S5's FFI surfaces. --mode={client¦connector} selects routing posture: client captures default route; connector advertises 10.10.0.0/24 and NAT-forwards decapsulated packets into veth-h. One binary per mode in Phase 0. |
| depends_on | HVPN-P0-008, HVPN-P0-012, HVPN-P0-016 |
| deliverable | helix-core/src/lib.rs + bin/helix-client.rs + bin/helix-connector.rs |
| acceptance | client orchestrator brings up plain-UDP WG to a second local orchestrator; ping <overlay-ip> succeeds; event stream emits Connected{plain-udp,rtt}; captured recording |
| est_effort | 1.0 |
| test_types | UT, IT, E2E, CONC, RACE |

The surviving status enum (mirrored across FFI in S5 [04_P0 §4.5/§9]):

// helix-core: the event the whole UX reads from
pub enum TunnelStatus {
    Connecting, Handshaking,
    Connected { transport: String, rtt_ms: u32 },
    Reconnecting, Down { reason: String },
}
// client:    [app traffic] → TUN → WG encrypt → Transport ──▶ gateway
// connector: gateway ──▶ Transport → WG decrypt → forward into 10.10.0.0/24 (and reverse)

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| Three async loops + broadcast event stream + TunnelStatus | HVPN-P0-019 | orchestrator | status transitions observed in test harness | UT, CONC, RACE |
| helix-client binary (default-route capture, plain-UDP up) | HVPN-P0-020 | bin/helix-client.rs | client↔gateway WG up; ping overlay (G1 partial) | IT, E2E |
| helix-connector binary (--mode=connector, advertise + NAT-forward) | HVPN-P0-021 | bin/helix-connector.rs | decapsulated packets reach veth-h and reverse | IT, E2E |

## 5. Milestone S2 — Connector advertise + two-way reach test (HVPN-P0-022..027) · G1

Proves: the two-way routing slice — connector advertises 10.10.0.0/24 (a netns LAN); client reaches 10.10.0.20:80. Effort: ~3d. Closes G1.

### TASK HVPN-P0-022 — netns + nftables + netem reproducible test rig

| Field | Value |
| --- | --- |
| parent | S2 |
| kind | task · type Task |
| title | Stand up the reproducible netns LAN + DPI + impairment test rig |
| gate | G1 (and G2 prep) |
| description | Linux network namespaces simulate the connector's private LAN and a remote service so the whole slice runs on one box and is CI-scriptable later [04_P0 §3]. Three processes: client, gateway, connector. Includes the nft DPI table (for G2) and tc netem impairment (for G2 loss tests), parked but installed here. |
| depends_on | HVPN-P0-021 |
| deliverable | rig/netns_up.sh, rig/netns_down.sh, rig/dpi_block.sh, rig/impair.sh |
| acceptance | rig/netns_up.sh creates lanA with a live http.server on 10.10.0.20:80; idempotent teardown; captured ip netns exec lanA curl localhost |
| est_effort | 1.0 |
| test_types | IT, FA, SEC |

The rig (concrete commands [04_P0 §3], to be wrapped in rig/*.sh):

# rig/netns_up.sh — connector-side "private LAN" simulated with a netns
sudo ip netns add lanA
sudo ip link add veth-h type veth peer name veth-lanA
sudo ip link set veth-lanA netns lanA
sudo ip addr add 10.10.0.1/24 dev veth-h               # connector host side
sudo ip -n lanA addr add 10.10.0.20/24 dev veth-lanA   # the "service" host
sudo ip link set veth-h up
sudo ip -n lanA link set veth-lanA up
sudo ip -n lanA route add default via 10.10.0.1
sudo ip netns exec lanA python3 -m http.server 80 --bind 10.10.0.20 &   # the hello service

# rig/dpi_block.sh — DPI/censorship sim for G2: kill plain WG UDP, allow 443
sudo nft add table inet dpi
sudo nft add chain inet dpi fwd '{ type filter hook forward priority 0; }'
sudo nft add rule inet dpi fwd udp dport 51820 drop
sudo nft add rule inet dpi fwd udp dport 443 accept

# rig/impair.sh — impairment for loss-resilience (G2)
sudo tc qdisc add dev "$IFACE" root netem loss 5% delay 40ms 10ms

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| netns LAN + hello-service up/down scripts | HVPN-P0-023 | netns_up.sh/netns_down.sh | LAN reachable from host; clean teardown leaves no orphan (§11.4.14) | IT, FA |
| nft DPI table + tc netem scripts (installed, parked for G2) | HVPN-P0-024 | dpi_block.sh/impair.sh | nft list ruleset shows drop:51820/accept:443; netem applied | IT, SEC |

### TASK HVPN-P0-025 — Two-way routing reach test (G1 close)

| Field | Value |
| --- | --- |
| parent | S2 |
| kind | task · type Feature |
| title | Prove client reaches connector LAN host through the full plain-UDP chain |
| gate | G1 |
| description | Success = curl from the client's overlay namespace to http://10.10.0.20/ returns the hello page, over plain-UDP [04_P0 §3]. This is the literal G1 close: real traffic client→gateway→connector LAN, both directions. |
| depends_on | HVPN-P0-020, HVPN-P0-023 |
| deliverable | rig/test_reach.sh + captured curl output + iperf3 CSV |
| acceptance | curl http://10.10.0.20/ returns hello page; iperf3 through-tunnel ≥ 80% bare link; deterministic over N=3 (§11.4.50); CSV + recording captured → gates.G1.outcome='pass' |
| est_effort | 1.0 |
| test_types | E2E, IT, FA, BENCH, SC, CH, HQA |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| Reach + return-path E2E (curl both directions) | HVPN-P0-026 | test_reach.sh | hello page returned; reverse path works | E2E, IT |
| iperf3 throughput vs bare-link baseline (≥80%) + roam/flap chaos | HVPN-P0-027 | iperf3 CSV row | ≥80% bar met; recovery <3s on iface flap (§11.4.85) | BENCH, SC, FA, CH |

## 6. Milestone S3 — MASQUE / QUIC transport (HVPN-P0-028..038) · G2 ⚠ high-risk

Proves: the QUIC headline — same slice over :443/udp HTTP/3; works through a UDP-block rule. Effort: ~5d. The riskiest Rust bet [04_P0 §5, §13].

Byte flow [04_P0 §5.1, research-masque]: WG datagram → HTTP Datagram (RFC 9297, ctx-id=0) → QUIC DATAGRAM frame (RFC 9221, unreliable) → QUIC/H3 to https://gateway:443 → edge extracts → WG datagram → kernel WG. The CONNECT-UDP request (RFC 9298) establishes the proxied UDP flow once; thereafter WG datagrams ride as HTTP Datagrams — no per-packet HTTP round trip. WG datagrams are independent & loss-tolerant ⇒ carry over QUIC DATAGRAM frames, never a QUIC stream (avoids head-of-line blocking) — getting this right is half the point of S3 (I2).

### TASK HVPN-P0-028 — quinn + h3 QUIC/HTTP-3 connection with unreliable datagrams

| Field | Value |
| --- | --- |
| parent | S3 |
| kind | task · type Feature |
| title | Establish a quinn QUIC/HTTP-3 connection exposing unreliable datagrams |
| gate | G2 |
| description | quinn (mature QUIC, exposes send_datagram/read_datagram) + h3 (HTTP/3 on quinn, less battle-tested than Go's stack) [04_P0 §5.2, research-quinn]. Stand up the QUIC/H3 connection to gw:443 and verify unreliable datagram exchange before layering MASQUE framing. |
| depends_on | HVPN-P0-006 |
| deliverable | helix-transport/src/masque.rs (connection setup) |
| acceptance | QUIC/H3 handshake to a local quinn server; send_datagram/read_datagram round-trips a 1200-byte payload; tshark shows QUIC long/short headers |
| est_effort | 1.5 |
| test_types | UT, IT, SEC |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| quinn client+server endpoints + TLS/SNI config | HVPN-P0-029 | endpoint setup | handshake completes; SNI = masquerade host | IT, SEC |
| Unreliable datagram round-trip (send_/read_datagram) | HVPN-P0-030 | datagram path | 1200-byte payload round-trips; no stream used | UT, IT |

### TASK HVPN-P0-031 — MASQUE CONNECT-UDP + HTTP-Datagram framing (the hand-rolled bet)

| Field | Value |
| --- | --- |
| parent | S3 |
| kind | task · type Feature |
| title | Hand-roll CONNECT-UDP and HTTP-Datagram framing over h3 + quinn datagrams |
| gate | G2, G4 |
| description | In Rust, turnkey MASQUE/CONNECT-UDP is thin-to-absent — expect to implement the CONNECT-UDP request (RFC 9298) + HTTP-Datagram framing (RFC 9297) by hand on top of h3 + quinn datagrams [04_P0 §5.2]. This relative immaturity vs Go's masque-go is itself a Phase-0 finding and a direct input to G4 (§7). Record effort hours + bespoke LOC. |
| depends_on | HVPN-P0-030 |
| deliverable | MasqueTransport impl + encode_http_datagram/decode_http_datagram |
| acceptance | full slice works end-to-end over MASQUE (no DPI yet); effort/LOC recorded into the G4 decision input; captured pcap shows HTTP Datagram framing |
| est_effort | 2.0 |
| test_types | UT, IT, E2E, SEC |

// helix-transport/src/masque.rs (the parts that matter) [04_P0 §5.2]
pub struct MasqueTransport { conn: quinn::Connection /* + CONNECT-UDP flow ctx from dial() */ }
#[async_trait]
impl Transport for MasqueTransport {
    async fn send(&self, wg: Bytes) -> Result<(), TransportError> {
        let http_dg = encode_http_datagram(/*ctx*/0, &wg);  // RFC 9297 framing
        self.conn.send_datagram(http_dg)?;                  // RFC 9221 QUIC datagram
        Ok(())
    }
    async fn recv(&self) -> Result<Bytes, TransportError> {
        let dg = self.conn.read_datagram().await?;
        Ok(decode_http_datagram(dg)?)                       // strip framing -> WG bytes
    }
    fn kind(&self) -> &'static str { "masque-h3" }
    fn effective_mtu(&self) -> u16 { 1280 }                 // QUIC overhead eats headroom; measure & tune
}

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| CONNECT-UDP request/response over h3 (RFC 9298) | HVPN-P0-032 | dial() Masque path | proxied UDP flow established to gw internal WG socket | UT, IT |
| HTTP-Datagram encode/decode (RFC 9297, ctx-id=0) + effective_mtu=1280 | HVPN-P0-033 | framing fns | WG bytes survive encode→decode identical; MTU tuned | UT, IT |
| Bespoke-MASQUE effort + LOC record (G4 input) | HVPN-P0-034 | decision/masque_effort.md | hours + LOC captured; honest §11.4.6 finding | CH, HQA |

### TASK HVPN-P0-035 — DPI-block survival + loss resilience + wire-fingerprint (G2 close)

| Field | Value |
| --- | --- |
| parent | S3 |
| kind | task · type Feature |
| title | Prove MASQUE survives a DPI UDP block, 5% loss, and looks like HTTP/3 |
| gate | G2 |
| description | S3 must demonstrate [04_P0 §5.3]: (1) slice works with plain WG UDP blocked (the nft rule) — real censorship evasion; (2) connection looks like HTTP/3 to a passive observer (tshark: QUIC headers, no WG signature, SNI = masquerade host); (3) loss resilience — under netem loss 5%, MASQUE/QUIC sustains higher goodput than a UDP-over-TCP strawman; (4) overhead quantified vs plain-UDP for the auto-ladder cost model. Edge serves a believable decoy site to non-CONNECT-UDP probes (native masquerade, §5.4). |
| depends_on | HVPN-P0-031, HVPN-P0-024 |
| deliverable | bench.sh MASQUE rows + tshark capture + decoy-page test |
| acceptance | with dpi_block.sh active, curl http://10.10.0.20/ still works over MASQUE; ≥50% of plain-UDP throughput; goodput@5%loss > UoT strawman; tshark classifies HTTP/3, no WG signature → gates.G2.outcome='pass' |
| est_effort | 1.5 |
| test_types | E2E, SEC, BENCH, SC, LOAD, CH, HQA, FA |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| End-to-end through DPI UDP block (51820 dropped, 443 allowed) | HVPN-P0-036 | reach test under DPI | hello page returned MASQUE-only | E2E, SEC, FA |
| Loss-resilience vs UoT strawman + overhead quantification | HVPN-P0-037 | bench.sh rows | MASQUE goodput@5% > UoT; overhead CSV captured | BENCH, SC, LOAD |
| Wire-fingerprint (tshark) + native decoy site for probes | HVPN-P0-038 | pcap + decoy page | classified HTTP/3, no WG sig; probe → decoy page | SEC, CH, HQA |

## 7. Milestone S4 — Go vs Rust gateway edge + A/B benchmark (HVPN-P0-039..048) · G4 ⚠

Proves: the edge decision — build both edges for MASQUE termination, decide on numbers [04_P0 §7]. Effort: ~4d. Identical job: terminate MASQUE on :443, hand WG to kernel WG.

|  | Rust edge (helix-edge) | Go edge |
| --- | --- | --- |
| QUIC/H3 | quinn + h3 (+ hand-rolled CONNECT-UDP) | quic-go + masque-go (turnkey CONNECT-UDP/IP) |
| Code reuse | Shares helix-transport byte-for-byte with clients | separate impl; must track the Rust one |
| Fits stack | new language in the server tree | matches the Go/Gin control plane exactly |
| Hot-path cost | no GC | GC pauses under load (measure) |
| MASQUE maturity | thinner ecosystem (a Phase-0 risk) | more mature MASQUE tooling |

### TASK HVPN-P0-039 — Rust edge helix-edge (MASQUE termination, shares helix-transport)

| Field | Value |
| --- | --- |
| parent | S4 |
| kind | task · type Feature |
| title | Build the Rust helix-edge terminating MASQUE and handing WG to kernel |
| gate | G4 |
| description | Rust contender [04_P0 §7.1]: reuses helix-transport byte-for-byte — the single-implementation guarantee; terminates MASQUE on :443, hands extracted WG datagrams to kernel WG / boringtun gateway socket. |
| depends_on | HVPN-P0-031 |
| deliverable | helix-edge/ Rust binary |
| acceptance | terminates the S3 client's MASQUE flow; slice reaches 10.10.0.20:80; captured reach test |
| est_effort | 1.0 |
| test_types | IT, E2E, SEC, RACE |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| MASQUE listener + WG handoff to kernel WG | HVPN-P0-040 | edge main | slice reaches LAN host via Rust edge | IT, E2E |
| Native decoy masquerade for non-flow probes | HVPN-P0-041 | decoy handler | probe → website; valid flow → tunnel | SEC |

### TASK HVPN-P0-042 — Go edge (quic-go + masque-go, turnkey CONNECT-UDP)

| Field | Value |
| --- | --- |
| parent | S4 |
| kind | task · type Feature |
| title | Build the Go edge with quic-go and masque-go for MASQUE termination |
| gate | G4 |
| description | Go contender [04_P0 §7.1]: quic-go + masque-go turnkey CONNECT-UDP/IP; matches the Go/Gin control plane exactly. Same job as the Rust edge for a fair A/B. |
| depends_on | HVPN-P0-024 |
| deliverable | go-edge/ Go binary |
| acceptance | terminates the same MASQUE flow; slice reaches 10.10.0.20:80; -race clean |
| est_effort | 1.0 |
| test_types | IT, E2E, SEC, RACE |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| quic-go + masque-go termination + WG handoff | HVPN-P0-043 | go edge main | slice reaches LAN host via Go edge | IT, E2E |
| go test -race + dev-cost hours record (G4 input) | HVPN-P0-044 | decision/go_effort.md | -race clean; hours-to-correct-CONNECT-UDP captured | RACE, CH |

### TASK HVPN-P0-045 — bench.sh A/B harness + decision matrix (G4 close)

| Field | Value |
| --- | --- |
| parent | S4 |
| kind | task · type Feature |
| title | Run the identical A/B benchmark and record the edge-language decision |
| gate | G4 |
| description | One harness, both edges, same rig, same kernel-WG backend [04_P0 §7.2]: throughput (1/10/100 clients), CPU per Gbps (cost-to-serve), p50/p99 RTT (Go GC tail), connection churn (handshakes/sec), memory under churn, dev cost. Fill the decision matrix; record the call in the decision log (§12). Default lean: Rust if within ~10–15% on throughput/CPU and hand-rolled CONNECT-UDP isn't a quagmire (single-impl win); else Go + accept dual MASQUE impls (mitigated by shared test vectors + conformance suite). |
| depends_on | HVPN-P0-040, HVPN-P0-043 |
| deliverable | bench.sh + results/edge_ab.csv + filled decision matrix |
| acceptance | CSV with CPU/Gbps, p99, churn, memory for both edges over N=3 (§11.4.50); decision recorded → gates.G4.outcome IN ('rust','go') with evidence path |
| est_effort | 1.5 |
| test_types | BENCH, LOAD, SC, FA, CH, HQA |

bench.sh outline (one script drives S4 A/B and S7 transport pair → CSV [04_P0 §8]):

#!/usr/bin/env bash
# bench.sh — comparable results for every transport × edge combination. Outputs one CSV row/run.
set -euo pipefail
EDGE="$1"          # rust-edge | go-edge
TRANSPORT="$2"     # plain-udp | masque-h3
CLIENTS="${3:-1}"  # 1 | 10 | 100
RUN="${4:-1}"      # iteration for §11.4.50 determinism (run N=3)
OUT="results/bench.csv"

bring_up_rig            # rig/netns_up.sh  (lanA + hello service)
start_edge   "$EDGE"    # exclusive owner of :443 (§11.4.119)
start_client "$TRANSPORT" --clients "$CLIENTS"

THRPUT=$(iperf3 -J -c 10.10.0.20 -P "$CLIENTS" | jq '.end.sum_received.bits_per_second')
ADDED_RTT_P50=$(ping_overlay_p50); ADDED_RTT_P99=$(ping_overlay_p99)
GOODPUT_LOSS=$(with_netem 'loss 5% delay 40ms' iperf3_goodput)   # G2 / SC
HS_TIME=$(timestamp_connect_to_first_data)
RECONNECT=$(flap_iface_time_to_recovery)                          # SC, <3s
CPU_PER_GBPS=$(pidstat_at_saturation "$EDGE")                     # cost-to-serve
EDGE_RSS=$(proc_rss_of "$EDGE")
CORE_RSS=$(proc_rss_of helix-client)                             # /proc; iOS via Instruments (§10)
FINGERPRINT=$(tshark_classify_flow)                              # http3 | wg-signature (SEC)

printf '%s,%s,%s,%s,%s,%s,%s,%s,%s,%s,%s,%s,%s\n' \
  "$RUN" "$EDGE" "$TRANSPORT" "$CLIENTS" "$THRPUT" "$ADDED_RTT_P50" "$ADDED_RTT_P99" \
  "$GOODPUT_LOSS" "$HS_TIME" "$RECONNECT" "$CPU_PER_GBPS" "$EDGE_RSS" "$FINGERPRINT" >> "$OUT"
tear_down_rig           # rig/netns_down.sh — leave quiescent (§11.4.14)

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| bench.sh harness + CSV schema (transport × edge × clients × run) | HVPN-P0-046 | bench.sh | runs all combos; deterministic CSV over N=3 | BENCH, FA |
| Throughput/CPU-per-Gbps/p99/churn/memory matrix fill | HVPN-P0-047 | edge_ab.csv | all six metrics captured both edges; churn under LOAD | BENCH, LOAD, SC |
| Decision-matrix scoring + decision-log entry (§12) | HVPN-P0-048 | decision/G4.md | weighted matrix → recorded call + consequence | CH, HQA |

## 8. Milestone S5 — flutter_rust_bridge FFI + Flutter-Linux toggle (HVPN-P0-049..054) · G5

Proves: the FFI boundary is clean enough to drive the core from Dart. Effort: ~3d. Use flutter_rust_bridge v2 — generates Dart⇄Rust glue, handles async + streams; the surface stays tiny and stable [04_P0 §9].

### TASK HVPN-P0-049 — helix-ffi flutter_rust_bridge v2 surface (survivor FFI)

| Field | Value |
| --- | --- |
| parent | S5 |
| kind | task · type Feature |
| title | Define the helix-ffi flutter_rust_bridge surface that survives into Phase 1 |
| gate | G5 |
| description | The FFI surface graduates into Phase 1 (gains policy/multi-hop fields) [04_P0 §14]. start(cfg) spins the orchestrator; stop() tears down; status_stream(sink) forwards the §4.5 broadcast channel; TunnelStatus mirrored via #[frb(mirror)]. |
| depends_on | HVPN-P0-019 |
| deliverable | helix-ffi/src/api.rs + generated Dart bindings |
| acceptance | flutter_rust_bridge_codegen produces Dart bindings that compile; start/stop/status_stream callable from a Dart unit test |
| est_effort | 1.5 |
| test_types | UT, IT |

// helix-ffi/src/api.rs — flutter_rust_bridge v2 generates Dart bindings [04_P0 §9]
pub struct ClientConfig { pub map_path: String, pub transport: String /* auto|plain|masque */ }
pub async fn start(cfg: ClientConfig) -> anyhow::Result<()> { /* spin up helix-core orchestrator */ }
pub async fn stop() -> anyhow::Result<()> { /* tear down */ }
/// Live status as a stream the UI subscribes to (maps to the §4.5 broadcast channel).
pub fn status_stream(sink: StreamSink<TunnelStatus>) { /* forward core events */ }
#[frb(mirror)]
pub enum TunnelStatus {
    Connecting, Handshaking,
    Connected { transport: String, rtt_ms: u32 },
    Reconnecting, Down { reason: String },
}

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| start/stop/ClientConfig + codegen | HVPN-P0-050 | api.rs + bindings | Dart can call start/stop; codegen clean | UT, IT |
| status_stream + #[frb(mirror)] TunnelStatus | HVPN-P0-051 | stream binding | Dart receives mapped status events | UT, IT |

### TASK HVPN-P0-052 — Flutter-Linux toggle + live status chip (G5 close)

| Field | Value |
| --- | --- |
| parent | S5 |
| kind | task · type Feature |
| title | Ship a Flutter-Linux window with a connect toggle and live status chip |
| gate | G5 |
| description | G5 pass [04_P0 §9]: a Flutter-Linux window with one connect/disconnect toggle and a status chip going Connecting → Handshaking → Connected (masque, 23ms) driven only by the Rust event stream. On Linux the core drives the TUN directly; on mobile the platform shim owns the TUN and the same FFI drives logic. |
| depends_on | HVPN-P0-051, HVPN-P0-025 |
| deliverable | app_access/ minimal Flutter-Linux app |
| acceptance | window toggle brings tunnel up/down; chip updates live from the core stream; window-scoped recording (§11.4.159) showing the transition → gates.G5.outcome='pass' |
| est_effort | 1.0 |
| test_types | UT, E2E, FA, CH, HQA |

// app_access — the entire happy path the spike must show [04_P0 §9]
await HelixCore.start(ClientConfig(mapPath: '/etc/helix/map.json', transport: 'auto'));
HelixCore.statusStream().listen((s) => setState(() => status = s));  // live chip updates
// ...toggle off:
await HelixCore.stop();

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| Toggle button → start/stop wiring | HVPN-P0-053 | toggle widget | tunnel up/down from UI | E2E |
| StatusChip bound to statusStream + window-scoped capture | HVPN-P0-054 | chip widget + mp4 | chip shows Connected(masque, NNms); recording validated (§11.4.163) | E2E, FA, CH, HQA |

## 9. Milestone S6 — Android VpnService + JNI (HVPN-P0-055..060)

Proves: the mobile path is real — Android VpnService + JNI loads helix-core; tunnel up on a real phone. Effort: ~3d. (Prerequisite for S7's device work.)

### TASK HVPN-P0-055 — Android VpnService + JNI bridge to helix-core

| Field | Value |
| --- | --- |
| parent | S6 |
| kind | task · type Feature |
| title | Build the Android VpnService and JNI bridge loading the Rust helix-core |
| gate | — (mobile path; feeds G3) |
| description | Android VpnService owns the TUN fd; JNI loads helix-core .so (aarch64-linux-android); the platform shim feeds packets to the same orchestrator API [04_P0 §2 S6, §9 note]. UniFFI generates the Kotlin shim. |
| depends_on | HVPN-P0-019 |
| deliverable | shims/android/ app + libhelix_core.so |
| acceptance | app builds; VpnService establishes the TUN; JNI calls reach the core; captured adb logcat |
| est_effort | 1.5 |
| test_types | UT, IT, MEM |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| aarch64-linux-android staticlib + UniFFI Kotlin bindings | HVPN-P0-056 | .so + bindings | JNI call into core returns; builds in CI-less local | UT, IT |
| VpnService TUN ownership + packet pump to core | HVPN-P0-057 | VpnService impl | TUN fd handed to core; packets flow | IT, MEM |

### TASK HVPN-P0-058 — Tunnel up on a real Android phone (E2E reach)

| Field | Value |
| --- | --- |
| parent | S6 |
| kind | task · type Feature |
| title | Bring the tunnel up on a physical Android device and reach the LAN host |
| gate | — (feeds G3 transport memory baselines) |
| description | Real device, not emulator (memory/behaviour representative). Tunnel up, reach 10.10.0.20:80 via plain-UDP then MASQUE; dumpsys meminfo RSS recorded as an Android comparison point for the iOS gate. |
| depends_on | HVPN-P0-057, HVPN-P0-035 |
| deliverable | device recording + dumpsys meminfo capture |
| acceptance | curl/browser on phone reaches LAN host both transports; RSS captured; §11.4.144 device-availability followed during the run |
| est_effort | 1.5 |
| test_types | E2E, MEM, SC, CH, HQA |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| Plain-UDP + MASQUE reach on device | HVPN-P0-059 | device recording | LAN host reachable both transports | E2E, CH |
| dumpsys meminfo RSS sampling + roam chaos | HVPN-P0-060 | meminfo CSV | RSS captured; survives WiFi↔LTE roam (SC) | MEM, SC, HQA |

## 10. Milestone S7 — iOS NEPacketTunnelProvider + memory harness (HVPN-P0-061..070) · G3 ⚠ make-or-break

Proves: the make-or-break gate — Rust core lives inside a NEPacketTunnelProvider under its memory budget with headroom. Effort: ~4d. If the core can't live in the NE, the "Rust core on every platform" thesis is wounded [04_P0 §6].

The constraint [04_P0 §6.1]: a Network Extension's packet-tunnel process runs with a far tighter memory budget than the host app — historically ~15 MB, raised on newer iOS but still strict and silently fatal: exceed it and iOS kills the extension, dropping the tunnel. The exact ceiling is device/OS-dependent and MUST be measured, not assumed (§11.4.6). This tight budget is the single strongest reason the data plane is Rust (no GC, bounded allocations) rather than Go (D2 [SYNTHESIS]).

### Harness layout [04_P0 §6.2]

ios-spike/
├── HelixTunnel/                 # NEPacketTunnelProvider (Swift)
│   └── PacketTunnelProvider.swift
├── libhelix_core.a              # Rust staticlib, aarch64-apple-ios, --release + LTO + strip
└── helix_core.h                 # cbindgen header (or UniFFI-generated)

// PacketTunnelProvider.swift (skeleton) [04_P0 §6.2]
import NetworkExtension
class PacketTunnelProvider: NEPacketTunnelProvider {
  override func startTunnel(options: [String:NSObject]?, completionHandler: @escaping (Error?)->Void) {
    // 1. configure NEPacketTunnelNetworkSettings (overlay IP, routes, DNS)
    // 2. helix_core_start(config)         // Rust core takes over packetFlow read/write
    // 3. pump: packetFlow.readPackets -> helix_core_tun_out;  core -> packetFlow.writePackets
  }
}

### TASK HVPN-P0-061 — iOS staticlib build (size-optimised) + cbindgen/UniFFI header

| Field | Value |
| --- | --- |
| parent | S7 |
| kind | task · type Feature |
| title | Build the size-optimised aarch64-apple-ios staticlib and FFI header |
| gate | G3 |
| description | Build the same helix-core as aarch64-apple-ios staticlib: opt-level=z/s + LTO + panic=abort + strip; record binary size [04_P0 §6.3]. cbindgen (or UniFFI) generates helix_core.h. Binary size is itself a recorded finding. |
| depends_on | HVPN-P0-014, HVPN-P0-019 |
| deliverable | libhelix_core.a + helix_core.h + size report |
| acceptance | staticlib builds for aarch64-apple-ios; size recorded; symbols stripped; captured size output |
| est_effort | 1.0 |
| test_types | UT, MEM, BENCH |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| Release profile (opt-level=z, LTO, panic=abort, strip) | HVPN-P0-062 | Cargo.toml profile | builds; size captured | UT, BENCH |
| cbindgen/UniFFI header helix_core.h (helix_core_start/_tun_out) | HVPN-P0-063 | header | header compiles in Xcode; symbols resolve | UT, MEM |

### TASK HVPN-P0-064 — NEPacketTunnelProvider skeleton + packetFlow pump

| Field | Value |
| --- | --- |
| parent | S7 |
| kind | task · type Feature |
| title | Wire the NEPacketTunnelProvider to drive the Rust core via packetFlow |
| gate | G3 |
| description | Configure NEPacketTunnelNetworkSettings (overlay IP, routes, DNS); helix_core_start(config); pump packetFlow.readPackets → helix_core_tun_out and core → packetFlow.writePackets [04_P0 §6.2]. The shim owns the TUN; the Rust core owns the datapath. |
| depends_on | HVPN-P0-063 |
| deliverable | ios-spike/HelixTunnel/PacketTunnelProvider.swift |
| acceptance | tunnel establishes on a real device; curl/Safari reaches 10.10.0.20:80 over plain-UDP; captured device recording |
| est_effort | 1.0 |
| test_types | IT, E2E, MEM |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| NEPacketTunnelNetworkSettings config + startTunnel | HVPN-P0-065 | provider | tunnel up; routes/DNS applied | IT, E2E |
| packetFlow ⇄ core pump (read/write) | HVPN-P0-066 | pump loop | LAN host reachable on device, plain-UDP | E2E, MEM |

### TASK HVPN-P0-067 — Memory harness: 1 GB / 30-min soak, both transports (G3 verdict)

| Field | Value |
| --- | --- |
| parent | S7 |
| kind | task · type Feature |
| title | Run the rigorous iOS memory soak deciding the Rust-on-every-platform thesis |
| gate | G3 |
| description | Be rigorous — this number decides architecture [04_P0 §6.3]. Drive a sustained 1 GB transfer through the tunnel on a real device (Simulator memory is not representative). Sample the extension process RSS via Xcode Instruments (Allocations + VM Tracker), not the host app — peak and steady-state. Run plain-UDP and MASQUE separately (QUIC buffers cost more memory; both must pass). Pass: steady-state peak under the device-enforced ceiling with ≥30% headroom for both transports across a 30-minute soak. If it fails [04_P0 §6.4], record fallback ladder: (1) shrink buffers / cap QUIC flow-control windows in the iOS build; (2) move MASQUE off-device for iOS (plain WG + on-path obfs only — partial feature loss); (3) split the core so only the lean WG datapath is in-extension, QUIC negotiation in the app via app-extension IPC. Each fallback is a real product decision. |
| depends_on | HVPN-P0-066, HVPN-P0-035 |
| deliverable | ios-spike/memory_report.md (peak/steady RSS, both transports, 30-min) + Instruments trace |
| acceptance | RSS report shows steady-state peak vs ceiling + headroom % for plain-UDP and MASQUE; verdict recorded → gates.G3.outcome IN ('pass','fail'); if fail, the §6.4 ladder choice is recorded (§11.4.112-style honest finding) |
| est_effort | 2.0 |
| test_types | MEM, SC, BENCH, FA, CH, HQA |

The honest-procedure checklist (each is a falsifiable evidence row, §11.4.5/.107):

- Build same-core staticlib (size-optimised) — done in HVPN-P0-062.

- Real device, not Simulator — recorded device serial (§11.4.144 followed).

- Sustained 1 GB transfer through tunnel — iperf3/bulk HTTP via the rig.

- Instruments on the extension process (Allocations + VM Tracker) — peak + steady RSS.

- Plain-UDP run AND MASQUE run, 30-min soak each.

- Pass = steady peak < ceiling with ≥30% headroom, both transports.

- On fail → record §6.4 fallback ladder choice as the architectural consequence.

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| Plain-UDP 30-min/1 GB soak + Instruments RSS | HVPN-P0-068 | trace + RSS row | steady peak + headroom % captured (plain) | MEM, SC, BENCH |
| MASQUE 30-min/1 GB soak + Instruments RSS | HVPN-P0-069 | trace + RSS row | steady peak + headroom % captured (masque) | MEM, SC, BENCH |
| Verdict + §6.4 fallback-ladder decision record (G3) | HVPN-P0-070 | memory_report.md | go/no-go recorded with headroom; ladder choice if fail | CH, HQA, FA |

## 11. Milestone S8 — Static network-map ingest + reconcile (HVPN-P0-071..076) · G6

Proves: the real-time model — fake the Go control plane with a file of the exact shape Phase 1's WatchNetworkMap will stream, so the reconciler is real [04_P0 §10]. Effort: ~2d. The literal seed of the Phase-1 push model.

// /etc/helix/map.json — the desired-state document the core reconciles to [04_P0 §10]
{
  "self":    { "overlay_ip": "fd7a:helix:1::2/128", "transport": "auto" },
  "gateway": { "endpoint": "gw.example:443", "wg_pubkey": "…", "masque_sni": "cdn.example" },
  "peers":   [ { "name": "connectorA", "wg_pubkey": "…", "allowed_ips": ["10.10.0.0/24"] } ],
  "dns":     ["fd7a:helix:1::1"]
}

### TASK HVPN-P0-071 — map.json schema + reconciler diff engine

| Field | Value |
| --- | --- |
| parent | S8 |
| kind | task · type Feature |
| title | Define the map.json desired-state schema and the reconciler diff engine |
| gate | G6 |
| description | The file has the exact shape Phase 1's WatchNetworkMap protobuf streams [04_P0 §10, §14] — so the reconciler graduates unchanged. The reconciler diffs desired-vs-actual and converges (add/remove peers, switch transport) without restarting the process; a file-watch stands in for a stream event. |
| depends_on | HVPN-P0-019 |
| deliverable | helix-core/src/map.rs (schema + reconcile diff) |
| acceptance | reconciler computes minimal add/remove deltas from two map versions; unit-tested; no restart of unrelated state |
| est_effort | 1.0 |
| test_types | UT, CONC, RACE |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| map.json serde schema (self/gateway/peers/dns) | HVPN-P0-072 | map.rs types | parses the §10 document; shape matches WatchNetworkMap | UT |
| Reconcile diff (desired vs actual peers/transport) + file-watch | HVPN-P0-073 | reconcile fn | minimal deltas; idempotent; no full teardown | UT, CONC, RACE |

### TASK HVPN-P0-074 — Map-delta reconcile, no-restart, new network reachable (G6 close)

| Field | Value |
| --- | --- |
| parent | S8 |
| kind | task · type Feature |
| title | Prove a map delta brings a new network reachable without restart |
| gate | G6 |
| description | G6 pass [04_P0 §10]: edit map.json to add the connector's prefix → the core picks up the delta (file-watch standing in for a stream event) and the client can now reach 10.10.0.20 — no restart, no reconnect of unrelated state. |
| depends_on | HVPN-P0-073, HVPN-P0-025 |
| deliverable | rig/test_reconcile.sh + before/after reach recording |
| acceptance | before: curl 10.10.0.20 fails (no peer); after map edit: succeeds, same process PID, tunnel never dropped → gates.G6.outcome='pass' |
| est_effort | 1.0 |
| test_types | E2E, IT, FA, SC, CH, HQA |

| Subtask | id | deliverable | acceptance | test_types |
| --- | --- | --- | --- | --- |
| Add-peer delta → reachable, PID unchanged | HVPN-P0-075 | reconcile test | new prefix reachable; same PID; no flap | E2E, IT, FA |
| Remove-peer delta + chaos (corrupt map mid-edit) | HVPN-P0-076 | chaos test | bad map rejected, last-good kept (§11.4.85) | SC, CH, HQA |

## 12. Cross-cutting deliverables (HVPN-P0-077..080)

These span all milestones — the harness, the decision log, the DB/CI wiring, and the Helix-ecosystem infra. They are Phase-0 definition-of-done items [04_P0 §11].

### TASK HVPN-P0-077 — Unified measurement harness + comparable CSV methodology

| Field | Value |
| --- | --- |
| parent | — |
| kind | task · type Task |
| title | Provide the unified measurement methodology and comparable CSV outputs |
| gate | G1, G2, G4 |
| description | One harness, run for every transport × edge combination so results are comparable [04_P0 §8]: throughput, added latency (p50/p99), loss resilience, handshake time, reconnect/roam, edge CPU/Gbps, core RSS per platform, wire fingerprint. bench.sh (HVPN-P0-046) is the engine; this item owns the methodology + pass bars as the single comparable contract so the decision tables fill themselves. |
| depends_on | HVPN-P0-046 |
| deliverable | docs/spike/measurement.md (the §8 metric table as a contract) |
| acceptance | every gate's numbers trace to a methodology row; pass-bars match §1; CSV columns stable |
| est_effort | 0.5 |
| test_types | BENCH, FA, CH |

Measurement contract [04_P0 §8] (the pass bars the CSV is judged against):

| Metric | How | Pass bar |
| --- | --- | --- |
| Through-tunnel throughput | iperf3 -c <lan-host-via-tunnel> (TCP+UDP) | plain-UDP ≥80% bare link; MASQUE ≥50% of plain-UDP |
| Added latency | ping overlay vs bare; p50/p99 | plain-UDP <2 ms; MASQUE <15 ms added |
| Loss resilience | tc netem loss 5% delay 40ms; goodput | MASQUE/QUIC > UoT strawman |
| Handshake time | connect→first-data | <1 s plain; <2 s MASQUE |
| Reconnect/roam | flap client iface; time to recovery | <3 s |
| Edge CPU per Gbps | pidstat/perf at saturation | record (cost-to-serve) |
| Core RSS per platform | /proc (Linux), Instruments (iOS), dumpsys (Android) | iOS gate per §10 |
| Wire fingerprint | tshark of MASQUE flow | classified HTTP/3, no WG signature |

### TASK HVPN-P0-078 — Decision log + 5-minute demo script

| Field | Value |
| --- | --- |
| parent | — |
| kind | task · type Task |
| title | Maintain the gate decision log and the narrated five-minute demo script |
| gate | G1–G6 |
| description | The decision log (§13) records G1–G6 outcomes + the edge call; the demo script narrates: plain-UDP slice → block WG → MASQUE survives → flip a map entry → new network reachable [04_P0 §11.7-8, §12]. Decision log is the authoritative Phase-0→Phase-1 entry record. |
| depends_on | HVPN-P0-048, HVPN-P0-070, HVPN-P0-074 |
| deliverable | docs/spike/decision_log.md + docs/spike/demo.md + recording |
| acceptance | all six gate rows filled with evidence paths; demo recording validated (§11.4.163); gates table all non-pending |
| est_effort | 0.5 |
| test_types | CH, HQA, FA |

### TASK HVPN-P0-079 — Workable-items DB seed + docs_chain sync

| Field | Value |
| --- | --- |
| parent | — |
| kind | task · type Task |
| title | Seed the workable-items SQLite DB from this WBS and wire docs_chain sync |
| gate | — |
| description | This WBS is the single source for docs/workable_items.db (§11.4.93/.95). Seed every HVPN-P0-NNN row + the six gates; wire docs_chain (§11.4.106) so md↔DB stay byte-identical (no force-push, §11.4.113; git-tracked DB, §11.4.95). |
| depends_on | HVPN-P0-002 |
| deliverable | seeded docs/workable_items.db + .docs_chain/contexts/phase0.yaml |
| acceptance | workable-items validate passes; md→db→md round-trip byte-identical; DB committed (tracked) |
| est_effort | 0.5 |
| test_types | UT, IT, FA |

### TASK HVPN-P0-080 — make spike one-shot + containers-submodule integration infra

| Field | Value |
| --- | --- |
| parent | — |
| kind | task · type Task |
| title | Wrap the whole rig in make spike on rootless-Podman integration infra |
| gate | G1, G2 |
| description | The reproducible rig + DPI-block + netem scripts run in one make spike [04_P0 §11.3]; integration infra (LAN sim hosts, edge containers) boots on-demand via the containers submodule (§11.4.76) in rootless Podman (§11.4.161) — no ad-hoc docker. Quadlet manifests describe the edge + connector containers. |
| depends_on | HVPN-P0-022, HVPN-P0-040, HVPN-P0-043 |
| deliverable | Makefile (make spike) + deploy/spike/*.container quadlets |
| acceptance | make spike runs S0–S2 + S3 slice headless, deterministic over N=3 (§11.4.50); infra booted via containers submodule; captured run log |
| est_effort | 1.0 |
| test_types | IT, FA, SC |

Rootless-Podman quadlet for the spike edge (boots on-demand, §11.4.76/.161):

# deploy/spike/helix-edge.container  — rootless Podman quadlet
[Unit]
Description=HelixVPN Phase-0 edge (MASQUE termination)
After=network-online.target

[Container]
Image=localhost/helix-edge:spike
PublishPort=443:443/udp
AddCapability=NET_ADMIN
ReadOnly=true
NoNewPrivileges=true
# rootless: no root, no sudo, no SSH on edge (§7 security invariants)

[Service]
Restart=on-failure

[Install]
WantedBy=default.target

## 13. Decision log (fill as gates clear) [04_P0 §12]

| Gate | Outcome | Evidence (numbers / capture) | Decision / consequence | Items |
| --- | --- | --- | --- | --- |
| G1 plain-UDP slice | ☐ pass ☐ fail | iperf … , ping/curl … | — | HVPN-P0-025/-027 |
| G2 MASQUE through DPI block | ☐ pass ☐ fail | goodput@5% loss … , tshark … | obfuscation D1 confirmed | HVPN-P0-035/-038 |
| G3 iOS memory | ☐ pass ☐ fail | peak RSS … / ceiling … / headroom … % | core stays Rust ↔ §6.4 fallback ladder | HVPN-P0-067/-070 |
| G4 edge language | ☐ Rust ☐ Go | CPU/Gbps R:… G:… ; p99 R:… G:… ; MASQUE effort … | single-impl ↔ dual-impl (D5) | HVPN-P0-045/-048 |
| G5 FFI | ☐ pass ☐ fail | demo recording | frb v2 ↔ UniFFI | HVPN-P0-052/-054 |
| G6 reconcile | ☐ pass ☐ fail | map-delta → reachable, no restart | confirms push model | HVPN-P0-074/-076 |

## 14. Phase-0 risks + pre-planned fallbacks [04_P0 §13]

| Risk | Likelihood | Fallback | Item(s) | Decision re-opened (reversal criteria) |
| --- | --- | --- | --- | --- |
| MASQUE/CONNECT-UDP in Rust over budget | med-high | Prototype MASQUE first in Go (masque-go) to unblock G2, then port — and let that inform G4 toward Go | HVPN-P0-031/-042 | D5 (edge language) — reversal fires if this pushes G4 toward Go per decision-register.md §2 D5 |
| boringtun quirks / maintenance gaps | med | Swap to wireguard-go via cgo for the spike, or kernel WG on Linux for non-iOS gates | HVPN-P0-011 | none registered (implementation swap, not a D-decision) |
| iOS NE memory fails | med | §6.4 ladder; worst case iOS ships plain-WG + on-path obfs only in v1 | HVPN-P0-067 | D2 (Rust core, make-or-break) — a captured G3 fail re-opens D2 and the whole client strategy per decision-register.md §2 D2 / §6 |
| h3 immaturity blocks datagrams | med | Pin versions; if blocked, carry WG over a QUIC stream as a stopgap (accept HoL blocking) purely to pass G2, flag non-final | HVPN-P0-028 | D1 (MASQUE primary) — a stopgap-stream G2 pass is provisional; genuine reversal needs a captured G2 fail per decision-register.md §2 D1 |
| Time-box blown | — | Stop; the unfinished gate is the finding — escalate the architectural decision with partial data (§11.4.6) rather than overrun silently | HVPN-P0-078 | whichever gate's decision (D1/D2/D5) is left unresolved stays a recommendation, never a resolution, per decision-register.md §0 |

Traceability note. This risk register names the operational fallback per item; v00-meta/decision-register.md §1/§2/§6 is the canonical record of which program-level decision (D1/D2/D5) each Phase-0 gate resolves and the exact captured-evidence condition that would re-open it. The two documents are deliberately non-duplicative: this table is "what do we do Monday morning if a gate fails," the decision register is "which cross-cutting architectural call does that failure re-open, and under what evidence."

## 15. How Phase 0 feeds Phase 1 [04_P0 §14]

Every surviving interface graduates: the Transport trait (HVPN-P0-004) gains Shadowsocks/UoT/LWO impls; the static map.json shape (HVPN-P0-071) becomes the WatchNetworkMap protobuf streamed by the Go coordinator [02-control-plane, 03-protocol]; the FFI surface (HVPN-P0-049) gains policy/multi-hop fields [03-client-core-and-ui]; the winning edge (G4) becomes helix-edge in the monorepo [04_ARCH §11]; the bench.sh harness (HVPN-P0-046) becomes the CI-less local gate suite with the §8 bars as thresholds. Nothing built here is wasted if the interfaces hold — which is the entire discipline of Phase 0.

Constitution bindings applied: §11.4.44 (revision header), §11.4.54 (stable monotonic HVPN-P0-NNN ids), §11.4.91 (≥6-word self-contained titles), §11.4.93/.95 (this WBS is the git-tracked workable-items DB source; DDL in §0.3), §11.4.106 (docs_chain md↔DB sync), §11.4.169 (per-item test_types from the closed set; §0.4), §11.4.5/.69/.107 (every acceptance cites captured PHYSICAL evidence), §11.4.6 (no-guessing — measure, don't assume; gate fail = finding), §11.4.50 (deterministic N=3), §11.4.76/.161 (containers submodule + rootless Podman for integration infra), §11.4.119 (bench rig = single-owner exclusive resource), §11.4.144 (device-availability followed during device runs), §11.4.159/.163 (window-scoped validated recordings), §11.4.65/.153 (HTML+PDF[+DOCX] exports follow in refinement).