# HelixVPN — Phase 0 Spike Plan

# HelixVPN — Phase 0 Spike Plan

Revision: 1 Last modified: 2026-07-04T12:00:00Z Note: This is the original Claude-authored Phase-0 plan that seeded final/06-phase0-spike-wbs.md. It is kept as historical/primary-source reference ([04_P0] citations throughout the final/ set point here); 06-phase0-spike-wbs.md is the authoritative, independently-verified, DB-ready expansion (3-tier epic→task→subtask, concrete evidence methodology, risk register cross-referenced to v00-meta/decision-register.md) — where the two differ in level of detail, the final/ doc wins per SPECIFICATION.md's spine-authority rule. No content contradictions were found between this document and 06-phase0-spike-wbs.md during independent gap-analysis (2026-07-04).

Companion to: HelixVPN-Architecture-Refined.md Purpose of Phase 0: build the thinnest possible end-to-end slice that exercises every hard part of the architecture, so that the expensive decisions (iOS viability, edge language, MASQUE-in-Rust maturity, the FFI boundary) are made on measured evidence, not on slideware. Phase 0 produces throwaway-quality code on production-quality interfaces: the traits, FFI signatures, and wire contracts defined here are meant to survive into Phase 1; the implementations behind them are allowed to be ugly.

Phase 0 is time-boxed to ~3–4 focused weeks. If a gate can't be passed in that window, that is the finding — escalate the decision rather than grind.

## 0. The questions Phase 0 must answer (exit gates)

| # | Question | Gate (go / no-go) | Section |
| --- | --- | --- | --- |
| G1 | Can helix-core (Rust + boringtun) move real traffic through the gateway to a connector's LAN over plain UDP? | iperf3 through-tunnel ≥ 80% of bare-link throughput; ping to LAN host succeeds | §4, §8 |
| G2 | Can the same core do it over MASQUE/QUIC (WG-in-HTTP/3)? | Works through a DPI-style UDP block; ≥ 50% of plain-UDP throughput; survives 5% packet loss better than UoT | §5, §8 |
| G3 | Does the Rust core run inside an iOS NEPacketTunnelProvider under its memory budget with headroom? | Steady-state RSS stays under the device-enforced ceiling with ≥ 30% headroom during a 1 GB transfer | §6 |
| G4 | Go vs Rust for the gateway edge — which terminates MASQUE better, all-in? | Decision recorded with benchmark numbers + reuse/velocity assessment | §7 |
| G5 | Is the flutter_rust_bridge FFI boundary clean enough to drive the core from Dart (connect/disconnect/status stream)? | Flutter Linux app toggles the tunnel and shows live status via the core's event stream | §9 |
| G6 | Does push-based reconciliation work at all (static network-map → core brings up peers)? | Core consumes a map document and converges without restart | §10 |

A "no-go" on G3 or G4 changes the architecture, not just the schedule — that's exactly why they're in Phase 0.

## 1. The vertical slice (what we build, precisely)

One client, one gateway, one connector, one LAN host. Nothing else.

┌─────────────────┐         ┌──────────────────────────────┐         ┌─────────────────────┐
 │  CLIENT          │         │  GATEWAY (VPS or local VM)    │         │  CONNECTOR site      │
 │  helix-core      │         │  ┌────────────┐  ┌─────────┐ │         │  helix-core (advert) │
 │  + Linux TUN     │  WG     │  │ edge (Go   │  │ kernel  │ │  WG     │  + boringtun         │
 │  (then Android,  │◀═══════▶│  │ OR Rust)   │◀▶│ WG / netns│◀═══════▶│  advertises          │
 │   then iOS NE)   │ over    │  │ MASQUE term│  │ router  │ │ over    │  10.10.0.0/24        │
 │                  │ UDP or  │  └────────────┘  └─────────┘ │ UDP     │                      │
 │                  │ QUIC    │   static network-map file    │         │  ┌────────────────┐  │
 └─────────────────┘         └──────────────────────────────┘         │  │ svc 10.10.0.20 │  │
                                                                       │  │ (http "hello") │  │
                                                                       │  └────────────────┘  │
                                                                       └─────────────────────┘

In scope: WG tunnels both sides; plain-UDP and MASQUE transports; static network map (a YAML/JSON file, no Go control plane yet); a "reach 10.10.0.20:80 and get a hello page" success test; the FFI + one Flutter toggle; the iOS memory harness; the dual edge benchmark.

Explicitly out of scope for Phase 0: Postgres/Redis, the real control plane, policy engine, multi-tenant, Console UI beyond a toggle, Shadowsocks/UoT/LWO/DAITA, multi-hop, HarmonyOS/Aurora, key rotation, billing. Those are Phase 1+. Faking them with static files is the whole point.

## 2. Spike milestones (each independently demoable)

| ID | Milestone | Proves | Days (rough) |
| --- | --- | --- | --- |
| S0 | Cargo workspace + helix-transport trait + plain-UDP impl; loopback echo test | the abstraction compiles and round-trips | 2 |
| S1 | helix-core wraps boringtun; Linux client ↔ Linux gateway plain-UDP WG up; ping overlay IP | WG core works through our transport | 3 |
| S2 | Connector advertises 10.10.0.0/24 (netns LAN); client reaches 10.10.0.20:80 | the two-way routing slice (G1) | 3 |
| S3 | MASQUE transport (quinn): same slice over :443/udp HTTP/3; works through a UDP-block rule | the QUIC headline (G2) | 5 |
| S4 | Go edge (quic-go + masque-go) terminating the same MASQUE; A/B benchmark vs Rust edge | the edge decision (G4) | 4 |
| S5 | flutter_rust_bridge FFI; Flutter-Linux app: connect/disconnect + live status stream | the FFI boundary (G5) | 3 |
| S6 | Android VpnService + JNI loads helix-core; tunnel up on a phone | mobile path real | 3 |
| S7 | iOS NEPacketTunnelProvider + Rust static lib; memory harness under 1 GB transfer | the make-or-break gate (G3) | 4 |
| S8 | Static network-map ingest + reconcile (bring peer up from a map delta, no restart) | the real-time model (G6) | 2 |

S3, S4, S7 are the high-risk ones; sequence them so a failure surfaces early. S0–S2 are the foundation everything else stands on.

## 3. Test rig & topology (reproducible, no special hardware)

Use Linux network namespaces to simulate the connector's private LAN and a "remote service," so the entire slice runs on one Linux box (or two cheap VMs) and is fully scriptable in CI later.

# --- connector-side "private LAN" simulated with a netns ---
sudo ip netns add lanA
sudo ip link add veth-h type veth peer name veth-lanA
sudo ip link set veth-lanA netns lanA
sudo ip addr add 10.10.0.1/24 dev veth-h            # connector host side
sudo ip -n lanA addr add 10.10.0.20/24 dev veth-lanA # the "service" host
sudo ip link set veth-h up
sudo ip -n lanA link set veth-lanA up
sudo ip -n lanA route add default via 10.10.0.1
# run a trivial service the client will reach through the whole chain:
sudo ip netns exec lanA python3 -m http.server 80 --bind 10.10.0.20 &

# --- DPI/censorship simulation for G2: block plain WireGuard UDP, allow 443 ---
# (apply on the path between client and gateway to force MASQUE)
sudo nft add table inet dpi
sudo nft add chain inet dpi fwd '{ type filter hook forward priority 0; }'
sudo nft add rule inet dpi fwd udp dport 51820 drop      # kill plain WG
sudo nft add rule inet dpi fwd udp dport 443 accept      # allow QUIC/443

# --- impairment for loss-resilience tests (G2) ---
sudo tc qdisc add dev <iface> root netem loss 5% delay 40ms 10ms

Three processes total: client (helix-core), gateway (edge + kernel WG or boringtun + the static router into lanA), connector (helix-core advertising 10.10.0.0/24, sitting on veth-h). Success = curl from the client's overlay namespace to http://10.10.0.20/ returns the hello page, with plain-UDP and with plain-UDP blocked (MASQUE only).

## 4. helix-core — the Rust workspace (S0–S2)

The interfaces below are the ones meant to survive into Phase 1. Keep them stable; let the bodies be scrappy.

### 4.1 Workspace layout

helix-core/
├── Cargo.toml                  # [workspace]
├── crates/
│   ├── helix-transport/        # the pluggable obfuscation layer (shared client+edge+connector)
│   │   ├── src/lib.rs          #   Transport trait + registry
│   │   ├── src/plain_udp.rs    #   S0/S1
│   │   └── src/masque.rs       #   S3 (quinn + HTTP/3 datagrams)
│   ├── helix-wg/               # boringtun wrapper: handshake, encrypt/decrypt, timers
│   ├── helix-tun/              # OS tun device abstraction (Linux now; shims call in later)
│   ├── helix-core/             # orchestrator: ties tun <-> wg <-> transport; event stream
│   └── helix-ffi/              # flutter_rust_bridge surface (S5)
└── bin/
    ├── helix-client.rs         # Linux CLI client (S1/S2)
    └── helix-connector.rs      # Linux CLI connector (S2)

### 4.2 The transport trait (the single most important interface in the project)

Everything obfuscation-related hides behind this. plain_udp and masque implement it; the client, connector, and gateway edge all consume it. One trait, three consumers, N transports — this is the "single implementation" guarantee from the architecture doc made concrete.

// helix-transport/src/lib.rs
use async_trait::async_trait;
use bytes::Bytes;
use std::net::SocketAddr;

/// A bidirectional carrier for already-encrypted WireGuard datagrams.
/// The transport NEVER sees plaintext; it only changes how WG bytes look on the wire.
#[async_trait]
pub trait Transport: Send + Sync {
    /// Send one WG datagram toward the peer endpoint.
    async fn send(&self, datagram: Bytes) -> Result<(), TransportError>;

    /// Receive the next WG datagram from the peer (cancel-safe).
    async fn recv(&self) -> Result<Bytes, TransportError>;

    /// Human label for logs/metrics: "plain-udp", "masque-h3", "shadowsocks", ...
    fn kind(&self) -> &'static str;

    /// MTU the upper layer (WG) may use over this transport, after overhead.
    fn effective_mtu(&self) -> u16;
}

#[derive(Clone, Debug)]
pub enum TransportConfig {
    PlainUdp { peer: SocketAddr, bind: SocketAddr },
    Masque   { url: String, sni: String, bind: SocketAddr }, // https://gw:443
    // Phase 1+: Shadowsocks { .. }, UdpOverTcp { .. }, Lwo { .. }
}

/// Build a transport from config. The escalation ladder (auto mode) just
/// constructs the next variant on repeated handshake failure.
pub async fn dial(cfg: TransportConfig) -> Result<Box<dyn Transport>, TransportError> { /* ... */ }

Design note: WG datagrams are independent and loss-tolerant, so the transport carries unreliable datagrams, never an ordered byte stream. For MASQUE that means QUIC DATAGRAM frames (RFC 9221) via HTTP Datagrams, not a QUIC stream — this preserves WG's own loss semantics and avoids head-of-line blocking. Getting this right is half the point of S3.

### 4.3 Plain-UDP transport (S0/S1)

Trivial, but it validates the trait and gives the throughput baseline every other transport is measured against.

// helix-transport/src/plain_udp.rs
pub struct PlainUdp { sock: tokio::net::UdpSocket, peer: SocketAddr }

#[async_trait]
impl Transport for PlainUdp {
    async fn send(&self, dg: Bytes) -> Result<(), TransportError> {
        self.sock.send_to(&dg, self.peer).await?; Ok(())
    }
    async fn recv(&self) -> Result<Bytes, TransportError> {
        let mut buf = vec![0u8; 1500];
        let n = self.sock.recv(&mut buf).await?;
        buf.truncate(n); Ok(Bytes::from(buf))
    }
    fn kind(&self) -> &'static str { "plain-udp" }
    fn effective_mtu(&self) -> u16 { 1420 } // standard WG-over-IPv4
}

### 4.4 helix-wg (boringtun wrapper)

boringtun is the right Phase-0 choice: pure-Rust userspace WireGuard, no kernel module, runs identically on Linux/Android/iOS — which is exactly the iOS path (no kernel WG on iOS regardless). Wrap its Tunn state machine; pump its timer; route its four output verdicts.

// helix-wg/src/lib.rs  (sketch)
pub struct WgPeer { tunn: boringtun::noise::Tunn, /* keys, endpoint */ }

impl WgPeer {
    /// Inbound: bytes arrived from the transport -> maybe plaintext for the TUN,
    /// or a handshake reply to send back out the transport.
    pub fn handle_transport_in(&mut self, datagram: &[u8], scratch: &mut [u8]) -> WgVerdict { /* ... */ }
    /// Outbound: a plaintext IP packet from the TUN -> encrypted datagram for transport.
    pub fn handle_tun_out(&mut self, ip_pkt: &[u8], scratch: &mut [u8]) -> WgVerdict { /* ... */ }
    /// Call ~every 100–250ms: emits keepalives / rekeys.
    pub fn tick(&mut self, scratch: &mut [u8]) -> WgVerdict { /* ... */ }
}
// WgVerdict = WriteToTransport(Bytes) | WriteToTun(Bytes) | Nothing | Err

### 4.5 helix-core orchestrator + the connector mode

The orchestrator runs three loops: tun → wg → transport, transport → wg → tun, and timer tick. The connector is the same core with a different routing posture: instead of capturing the device's default route, it (a) advertises 10.10.0.0/24 in its map, and (b) NATs/forwards decapsulated packets into veth-h and back. One binary, a --mode={client|connector} flag in Phase 0.

client:    [app traffic] → TUN → WG encrypt → Transport ──▶ gateway
connector: gateway ──▶ Transport → WG decrypt → forward into 10.10.0.0/24 (and reverse)

The orchestrator also exposes an event stream (tokio::sync::broadcast) — Connecting | Handshaking | Connected{transport, rtt} | Reconnecting | Down{reason} — which is what the FFI surfaces to Flutter in S5 and what proves the "real-time status" UX.

## 5. MASQUE / QUIC transport (S3 — the headline, and the riskiest Rust bet)

This is where Phase 0 earns its keep. The goal: wrap each WireGuard datagram in an HTTP/3 CONNECT-UDP exchange (RFC 9298) so the flow on :443/udp is indistinguishable from a browser doing HTTP/3 — the exact mechanism Mullvad ships.

### 5.1 How the bytes flow

client WG datagram (Bytes)
   └▶ HTTP Datagram  (RFC 9297, context-id = 0 for UDP payload)
        └▶ QUIC DATAGRAM frame (RFC 9221, unreliable — matches WG semantics)
             └▶ QUIC/HTTP-3 connection to https://gateway:443  (looks like web)
                  └▶ edge: extract HTTP Datagram → WG datagram → kernel WG

The CONNECT-UDP request establishes the proxied UDP "flow" to the gateway's internal WG socket; thereafter WG datagrams ride as HTTP Datagrams over QUIC DATAGRAM frames. No per-packet HTTP round trip — the tunnel is set up once, then it's pure datagram relay.

### 5.2 Rust building blocks (and the maturity caveat)

- quinn — mature QUIC. Exposes unreliable datagrams (Connection::send_datagram/read_datagram). Solid.

- h3 — HTTP/3 on quinn. Exists, less battle-tested than Go's stack.

- MASQUE capsule/CONNECT-UDP handling — in Rust this is thin-to-absent as a turnkey crate; expect to implement the CONNECT-UDP request + HTTP-Datagram framing by hand on top of h3 + quinn datagrams. This relative immaturity vs Go's masque-go is itself a Phase-0 finding and a direct input to G4 (§7).

// helix-transport/src/masque.rs  (sketch — the parts that matter)
pub struct MasqueTransport {
    conn: quinn::Connection,        // established QUIC/H3 connection to gw:443
    // flow context for CONNECT-UDP established at dial()
}

#[async_trait]
impl Transport for MasqueTransport {
    async fn send(&self, wg: Bytes) -> Result<(), TransportError> {
        let http_dg = encode_http_datagram(/*ctx*/0, &wg); // RFC 9297 framing
        self.conn.send_datagram(http_dg)?;                  // RFC 9221 QUIC datagram
        Ok(())
    }
    async fn recv(&self) -> Result<Bytes, TransportError> {
        let dg = self.conn.read_datagram().await?;
        Ok(decode_http_datagram(dg)?)                       // strip framing -> WG bytes
    }
    fn kind(&self) -> &'static str { "masque-h3" }
    fn effective_mtu(&self) -> u16 { 1280 } // QUIC overhead eats headroom; measure & tune
}

### 5.3 What S3 must demonstrate

- Slice works end-to-end with plain WG UDP blocked (the nft rule from §3) — proving real censorship evasion, not just "QUIC also works."

- The connection looks like HTTP/3 to a passive observer (verify with a packet capture: QUIC long/short headers, no WG signature; ideally TLS SNI matching the masquerade host).

- Loss resilience: under netem loss 5%, MASQUE/QUIC sustains higher goodput than a UDP-over-TCP strawman — QUIC's loss recovery is the reason mobile got this feature.

- Overhead is quantified: record the MTU/throughput/CPU penalty vs plain UDP so the auto-ladder's cost model is real.

### 5.4 Masquerade (carry-forward, native)

The edge's :443 should serve a believable decoy site to anything that isn't a valid CONNECT-UDP flow (probes, scanners). Phase 0: a static "it's just a website" page behind the same QUIC listener. This replaces the original doc's Nginx-camouflage trick with a native edge behavior.

## 6. iOS memory-ceiling experiment (S7 — the make-or-break gate, G3)

If the core can't live inside a NEPacketTunnelProvider, the whole "Rust core on every platform" thesis is wounded — so we test it early-ish and honestly.

### 6.1 The constraint

A Network Extension's packet-tunnel process runs with a far tighter memory budget than the host app — historically cited around ~15 MB, raised on newer iOS for packet tunnel providers but still strict and silently fatal: exceed it and iOS kills the extension, dropping the tunnel. The exact ceiling is device/OS-dependent and must be measured, not assumed. This tight budget is the single strongest reason the data plane is Rust (no GC, bounded allocations) rather than Go.

### 6.2 Harness

ios-spike/
├── HelixTunnel/                 # NEPacketTunnelProvider (Swift)
│   └── PacketTunnelProvider.swift
├── libhelix_core.a              # Rust staticlib, aarch64-apple-ios, --release + LTO + strip
└── helix_core.h                 # cbindgen header (or UniFFI-generated)

// PacketTunnelProvider.swift (skeleton)
import NetworkExtension
class PacketTunnelProvider: NEPacketTunnelProvider {
  override func startTunnel(options: [String:NSObject]?, completionHandler: @escaping (Error?)->Void) {
    // 1. configure NEPacketTunnelNetworkSettings (overlay IP, routes, DNS)
    // 2. helix_core_start(config)   // Rust core takes over packetFlow read/write
    // 3. pump: packetFlow.readPackets -> helix_core_tun_out;  core -> packetFlow.writePackets
  }
}

### 6.3 Method (be rigorous — this number decides architecture)

- Build the same helix-core as aarch64-apple-ios staticlib, opt-level=z/s + LTO + panic=abort + strip; record binary size.

- Drive a sustained 1 GB transfer through the tunnel on a real device (Simulator memory behavior is not representative).

- Sample the extension process RSS via Xcode Instruments (Allocations + VM Tracker), not the host app. Record peak and steady-state.

- Run plain-UDP and MASQUE separately — QUIC buffers cost more memory; both must pass.

- Pass: steady-state peak stays under the device-enforced ceiling with ≥ 30% headroom for both transports across a 30-minute soak.

### 6.4 If it fails

Documented fallbacks, in order: (1) shrink buffers / cap QUIC flow-control windows in the iOS build; (2) move MASQUE off-device for iOS (client uses plain WG + on-path obfuscation only) — partial feature loss; (3) split the core so only the lean WG datapath is in-extension and QUIC negotiation lives in the app via app-extension IPC. Each fallback is a real product decision, which is why we surface it in Phase 0.

## 7. Go vs Rust gateway edge (S4 — decision G4)

The architecture doc recommends Rust (single MASQUE implementation shared with clients) but flags Go as acceptable. Phase 0 builds both for the MASQUE termination path and decides on numbers.

### 7.1 The two contenders (identical job: terminate MASQUE on :443, hand WG to kernel)

|  | Rust edge (helix-edge) | Go edge |
| --- | --- | --- |
| QUIC/H3 | quinn + h3 (+ hand-rolled CONNECT-UDP) | quic-go + masque-go (turnkey CONNECT-UDP/IP) |
| Code reuse | Shares helix-transport byte-for-byte with clients | Separate implementation; must track the Rust one |
| Fits stack | new language in the server tree | matches the Go/Gin control plane exactly |
| Hot-path cost | no GC | GC pauses under load (measure) |
| MASQUE maturity | thinner ecosystem (a Phase-0 risk) | more mature MASQUE tooling |

### 7.2 Benchmark protocol (run both, same rig, same kernel-WG backend)

- Throughput: iperf3 through-tunnel, 1 / 10 / 100 concurrent clients.

- CPU per Gbps at the edge (the cost-to-serve number).

- Latency: p50/p99 RTT added by the edge; for Go, watch GC-induced p99 tail.

- Connection churn: N handshakes/sec the edge sustains (mobile roaming = constant re-handshakes).

- Memory under churn.

- Dev cost (qualitative): hours to get CONNECT-UDP correct in each; lines of bespoke code.

### 7.3 Decision matrix (fill from S4 results)

| Criterion | Weight | Rust | Go |
| --- | --- | --- | --- |
| Reuse / single-impl guarantee | high | ✅ | ✗ |
| MASQUE implementation effort | high | ? | ✅ |
| Throughput & CPU/Gbps | high | ? | ? |
| p99 latency under load | med | ? | ? |
| Fits existing Go control plane | med | ✗ | ✅ |
| Team velocity | med | ? | ? |

Default lean: if Rust gets within ~10–15% on throughput/CPU and the hand-rolled CONNECT-UDP isn't a quagmire, choose Rust for the single-implementation win. If MASQUE-in-Rust proves painful or Go wins decisively on cost-to-serve, choose Go and accept dual MASQUE implementations (mitigated by sharing test vectors + a conformance suite across both). Record the call in the decision log (§12).

## 8. Measurement methodology (applies to G1, G2, G4)

One harness, run for every transport × edge combination so results are comparable.

| Metric | How | Pass bar |
| --- | --- | --- |
| Through-tunnel throughput | iperf3 -c <lan-host-via-tunnel> (TCP + UDP) | plain-UDP ≥ 80% bare link; MASQUE ≥ 50% of plain-UDP |
| Added latency | ping overlay vs bare; p50/p99 | plain-UDP < 2 ms added; MASQUE < 15 ms added |
| Loss resilience | tc netem loss 5% delay 40ms; compare goodput | MASQUE/QUIC > UoT strawman |
| Handshake time | timestamp connect→first-data | < 1 s plain; < 2 s MASQUE |
| Reconnect/roam | flap the client iface; time to recovery | < 3 s |
| Edge CPU per Gbps | pidstat/perf at saturation | record (cost-to-serve) |
| Core RSS (per platform) | /proc (Linux), Instruments (iOS), dumpsys meminfo (Android) | iOS gate per §6.3 |
| Wire fingerprint | tshark capture of MASQUE flow | classified as HTTP/3, no WG signature |

Script it (bench.sh) so S4's A/B and S7's transport pair run identically and land in a CSV → the decision tables fill themselves.

## 9. FFI boundary — Flutter ↔ Rust core (S5, gate G5)

Use flutter_rust_bridge v2: generates the Dart⇄Rust glue, handles async, and streams. The surface stays tiny and stable.

// helix-ffi/src/api.rs  (flutter_rust_bridge generates Dart bindings from this)
pub struct ClientConfig { pub map_path: String, pub transport: String /* auto|plain|masque */ }

pub async fn start(cfg: ClientConfig) -> anyhow::Result<()> { /* spin up helix-core orchestrator */ }
pub async fn stop() -> anyhow::Result<()> { /* tear down */ }

/// Live status as a stream the UI subscribes to (maps to the broadcast channel in §4.5).
pub fn status_stream(sink: StreamSink<TunnelStatus>) { /* forward core events */ }

#[frb(mirror)]
pub enum TunnelStatus {
    Connecting, Handshaking,
    Connected { transport: String, rtt_ms: u32 },
    Reconnecting, Down { reason: String },
}

// Flutter (app_access) — the entire happy path the spike must show:
await HelixCore.start(ClientConfig(mapPath: '/etc/helix/map.json', transport: 'auto'));
HelixCore.statusStream().listen((s) => setState(() => status = s)); // live chip updates
// ...toggle off:
await HelixCore.stop();

G5 pass: a Flutter-Linux window with one connect/disconnect toggle and a status chip that goes Connecting → Handshaking → Connected (masque, 23ms) driven only by the Rust event stream. On Linux the core can drive the TUN directly; on mobile the platform shim (S6/S7) owns the TUN and the same FFI drives logic.

## 10. Static network-map + reconciliation (S8, gate G6)

No Go control plane yet — fake it with a file that has the exact shape Phase 1's WatchNetworkMap will stream, so the reconciler is real even though the source is static.

// /etc/helix/map.json  — the desired-state document the core reconciles to
{
  "self":   { "overlay_ip": "fd7a:helix:1::2/128", "transport": "auto" },
  "gateway":{ "endpoint": "gw.example:443", "wg_pubkey": "…", "masque_sni": "cdn.example" },
  "peers":  [ { "name": "connectorA", "wg_pubkey": "…", "allowed_ips": ["10.10.0.0/24"] } ],
  "dns":    ["fd7a:helix:1::1"]
}

The reconciler diffs desired-vs-actual and converges (add/remove peers, switch transport) without restarting the process. G6 pass: edit map.json to add the connector's prefix → the core picks up the delta (file-watch standing in for a stream event) and the client can now reach 10.10.0.20 — no restart, no reconnect of unrelated state. This is the literal seed of the Phase-1 push model.

## 11. Deliverables (definition of done for Phase 0)

- helix-core Rust workspace: transport trait + plain-UDP + MASQUE, boringtun WG, TUN, orchestrator, client+connector binaries.

- Both edges (helix-edge Rust + Go edge) terminating MASQUE, with the bench.sh CSV comparing them.

- Reproducible netns rig + DPI-block + netem scripts (the §3 + §8 harness), runnable in one make spike.

- Flutter-Linux app proving the FFI toggle + live status (G5).

- Android build with the tunnel up on a real phone (S6).

- iOS NE build + the memory report (peak/steady RSS, both transports, 30-min soak) — the G3 verdict.

- Decision log (§12) with G1–G6 outcomes and the edge-language call.

- A 5-minute demo script: plain-UDP slice → block WG → MASQUE slice survives → flip a map entry → new network reachable, all narrated.

## 12. Decision log (fill as gates clear)

| Gate | Outcome | Evidence (numbers / capture) | Decision / consequence |
| --- | --- | --- | --- |
| G1 plain-UDP slice | ☐ pass ☐ fail | iperf …, ping … | — |
| G2 MASQUE through DPI block | ☐ pass ☐ fail | goodput @5% loss …, tshark … | — |
| G3 iOS memory | ☐ pass ☐ fail | peak RSS … / ceiling … / headroom … % | core stays Rust ↔ fallback §6.4 |
| G4 edge language | ☐ Rust ☐ Go | CPU/Gbps R:… G:…; p99 R:… G:…; MASQUE effort … | single-impl ↔ dual-impl |
| G5 FFI | ☐ pass ☐ fail | demo recording | frb v2 ↔ UniFFI |
| G6 reconcile | ☐ pass ☐ fail | map-delta → reachable, no restart | confirms push model |

## 13. Risks specific to Phase 0 (and pre-planned fallbacks)

| Risk | Likelihood | Fallback |
| --- | --- | --- |
| MASQUE/CONNECT-UDP in Rust takes longer than budget | med-high | Prototype MASQUE first in Go (masque-go) to unblock G2, then port — and let that inform G4 toward Go |
| boringtun quirks / maintenance gaps | med | Swap to wireguard-go via cgo for the spike, or kernel WG on Linux for non-iOS gates |
| iOS NE memory fails | med | §6.4 ladder; worst case iOS ships plain-WG + on-path obfs only in v1 |
| h3 immaturity blocks datagrams | med | Pin versions; if blocked, carry WG over a QUIC stream as a stopgap (accept HoL blocking) purely to pass G2, flag as non-final |
| Time-box blown | — | Stop; the unfinished gate is the finding. Escalate the architectural decision with partial data rather than overrun silently |

## 14. How Phase 0 feeds Phase 1

Every surviving interface graduates: the Transport trait gains Shadowsocks/UoT/LWO impls; the static map.json shape becomes the WatchNetworkMap protobuf streamed by the Go coordinator; the FFI surface gains policy/multi-hop fields; the winning edge becomes helix-edge in the monorepo (§11 of the architecture doc); the bench harness becomes CI gates with the §8 bars as thresholds. Nothing built here is wasted if the interfaces hold — which is the entire discipline of Phase 0.

End of Phase 0 spike plan. Pair with HelixVPN-Architecture-Refined.md §12 (roadmap) — clearing G1–G6 is the entry condition for Phase 1 (MVP self-host).