# Phase 1 (MVP) — Work Breakdown: phases → tasks → subtasks

# Phase 1 (MVP) — Work Breakdown: phases → tasks → subtasks

Revision: 2 Last modified: 2026-07-04T12:00:00Z Rev 2 (hardening pass): Added §0 cross-reference to v07-execution/subtask-deepening-p1.md (closes REFINEMENT_NOTES.md R5 — the PR-sized .k subtask breakdown for every Phase‑1 task lives there, not duplicated here); added §2.1 Mermaid sequence diagram for the enroll→reach→revoke flow (ties AC1/AC2/AC6/SLO2/SLO3 to the concrete event sequence); added §2.2 phase‑gate‑failure / rollback protocol.

This document is the executable spine of the HelixVPN MVP. It decomposes the Phase‑1 self‑hostable MVP into stable, DB‑ready work items (HVPN-P1-NNN), each carrying description · depends‑on · deliverable · acceptance · effort · required‑test‑types, grouped by control‑plane module + client core/UI + platform shims + deploy + QA. It is spec‑only — it describes what to build and how "done" is proven, never the product itself. Authoritative companions: the data model / DDL / protobuf live in 02-control-plane.md (cited here as [02]); the data plane in 01-data-plane.md [01]; the client core + UI in 03-client-core-and-ui.md [03]; security / privacy / PKI in 04-security-privacy-pki.md [04]; product scope in 00-product-scope-and-principles.md [00]. Primary research: [04_P1] (HelixVPN-Phase1-MVP.md), [04_P0] (HelixVPN-Phase0-Spike.md), [04_ARCH], [05_YBO], [SYNTHESIS].

PR-sized subtask breakdown (closes R5): every task HVPN-P1-NNN below is decomposed one level further — into falsifiable, PR-sized subtasks HVPN-P1-NNN.k with their own acceptance/tests/complexity — in the companion v07-execution/subtask-deepening-p1.md. This WBS stays at task granularity (already concrete: deliverable + acceptance

- tests per item); the .k decomposition is the R5-closing detail layer that feeds the workable-items DB (§3) at the same granularity Phase 0 uses.

## Table of contents

- 0. How to read this WBS

- 1. Required‑test‑types vocabulary (§11.4.169)

- 2. MVP Definition‑of‑Done — the 8 acceptance gates + SLOs

- 2.1 Enroll → reach → revoke sequence

- 2.2 Phase-gate-failure / rollback protocol

- 3. Workable‑item schema (§11.4.93 DB‑ready)

- 4. Epic map + dependency graph

- 5. Phase 0 — entry gates (prerequisite)

- 6. E01 — Foundation: repo, proto, codegen, CI floor

- 7. E02 — Store, schema, RLS, no‑log lint

- 8. E03 — Identity, enrollment, PKI

- 9. E04 — IPAM (D4)

- 10. E05 — Event backbone (D3)

- 11. E06 — Policy model & compiler

- 12. E07 — Coordinator & WatchNetworkMap

- 13. E08 — API surface + authz

- 14. E09 — helix‑core (Rust client/connector)

- 15. E10 — helix‑edge (data plane)

- 16. E11 — helix‑ui (Flutter) + design system

- 17. E12 — Platform tunnel shims (iOS/Android/Linux)

- 18. E13 — Deploy: helixvpnctl + Podman quadlets + containers submodule

- 19. E14 — QA, SLOs, DoD certification

- 20. E15 — Docs‑chain, workable‑items DB, release

- 21. DoD ↔ work‑item traceability matrix

- 22. Effort roll‑up & critical path

- Sources

## 0. How to read this WBS

Granularity. Three levels: Epic (HVPN-P1-Enn, a workstream) → Task (HVPN-P1-NNN, a shippable unit, ~1–8 person‑days) → Subtask (HVPN-P1-NNN.k, a single PR‑sized change). Every leaf (a task with no subtasks, or a subtask) is a workable item per §11.4.93 and is the unit that lands in the SQLite single‑source‑of‑truth DB (§3).

ID scheme (stable, append‑only, §11.4.54). HVPN-P1- prefix; the numeric block encodes the epic: Enn → tasks nn0..nn9, e.g. E02 (store) → 020..029. Phase‑0 entry gates use 001..006. IDs are never renumbered; new work appends at the next free number in the block (gaps allowed).

Field contract (every leaf).

| Field | Meaning |
| --- | --- |
| Desc | What the item builds, in one or two sentences (§11.4.91 ≥6 words / ≥40 chars). |
| Deps | Hard upstream item IDs (must be complete first). — = none. |
| Deliverable | The concrete artefact(s) — file paths, binaries, generated clients. |
| Acceptance | The falsifiable PASS condition, captured‑evidence per §11.4.5/.69/.107. |
| Effort | T‑shirt + person‑days: XS(1) S(2–3) M(4–6) L(7–10) XL(11–15). |
| Tests | Required test types from the §1 closed vocabulary (§11.4.169). |

Risk ordering (§11.4.132). Within and across epics, the irreversible correctness floor (RLS, no‑log lint, PKI revoke, kill‑switch) is sequenced first; convenience UI last.

Anti‑bluff (§11.4 / §11.4.27 / §11.4.107). Every Acceptance line is a captured‑evidence assertion, not "code compiles". A leaf is complete only when its required‑test‑types are green with an evidence path recorded in the item's test_diary (§11.4.149) and, where it has a user‑visible surface, a window‑scoped MP4 recording vision‑verified per §11.4.159/.163. Metadata‑only / config‑only / grep‑without‑runtime PASS is forbidden.

## 1. Required‑test‑types vocabulary (§11.4.169)

§11.4.169 mandates that every workable item declare the closed set of test types it must pass before closure; the universe of types is the §11.4.27 enumeration. The closed vocabulary + canonical abbreviations used in this WBS:

| Abbrev | Type | Floor expectation for HelixVPN MVP |
| --- | --- | --- |
| UNIT | Unit | pure logic (compiler, IPAM, delta diff, framing); mocks allowed only here (§11.4.27). |
| INT | Integration | real Postgres + Redis (testcontainers via containers submodule, §11.4.76); no mocks. |
| E2E | End‑to‑end | the netns rig [04_P0 §3] fed by the real control plane; curl reaches the LAN host. |
| FA | Full‑automation | self‑driving, re‑runnable -count=3, no human in the loop (§11.4.98). |
| SEC | Security | RLS cross‑tenant denial, key‑never‑leaves, mTLS, kill‑switch, DNS‑leak, secret‑leak audit (§04). |
| CHAOS | Chaos | mid‑flight SIGKILL / Redis drop / partial write; recovery restores consistent state (§11.4.85). |
| STRESS | Stress | sustained load + concurrency (≥10 parallel, ≥100 iters or ≥30 s) + boundary inputs (§11.4.85). |
| PERF | Performance | latency p50/p99 vs the SLO budget (§2); GC‑tail watch on Go hot paths. |
| BENCH | Benchmarking | throughput / CPU‑per‑Gbps / handshakes‑per‑sec on the bench.sh rig [04_P0 §8]. |
| SCALE | Scaling | N simulated agents holding streams; convergence + bounded memory over 24 h soak. |
| UI | UI | widget + golden tests on the three Flutter flavors. |
| UX | UX | flow walkthrough (enroll → connect → reach) with window‑scoped MP4 + vision verdict (§11.4.159). |
| REC | Recorded‑evidence | window‑scoped MP4 (§11.4.154/.155) + media‑validation pipeline verdict (§11.4.163). |
| CHAL | Challenge / HelixQA | a challenges / helix_qa bank entry scoring PASS only on captured evidence (§11.4.27/.107). |

DDOS is not‑applicable at MVP (single‑node self‑host, no public multi‑tenant surface) — explicitly recorded NOT_APPLICABLE: single-node-selfhost per §11.4.6, re‑armed in Phase 2 (HA / managed). Each task below lists only the required subset; absent types are out‑of‑scope for that item by design, not by omission.

## 2. MVP Definition‑of‑Done — the 8 acceptance gates + SLOs

The MVP ships only when all eight acceptance criteria (AC1–AC8) and all four SLOs (SLO1–SLO4) pass on a clean baseline (§11.4.40 full‑suite retest, §11.4.108 runtime‑signature on a fresh deploy). These are the release gates — restated verbatim from [04_P1 §11.2/§11.3] and bound to work‑items in §21.

AC8 in [04_P1] bundles "no durable log" with "three apps drive it"; this WBS splits the app‑coverage clause out as AC9 for traceability — both are required.

AC1 — Self‑host from zero. On a fresh rootless host, helixvpnctl init + systemctl --user start helixvpn-pod yields a running control plane + edge with generated tenant/admin/CA/overlay‑/48/creds. Evidence: recorded terminal session, healthchecks green, helix_up == 1.

AC2 — Authorized reachability. Enroll one connector advertising a LAN + one client; the client's overlay namespace curls an authorized LAN host and gets the hello page. Evidence: E2E netns capture + pcap.

AC3 — Default‑deny. The same client is denied a LAN host not granted by policy (connection refused/dropped at the edge verdict map). Evidence: negative E2E — packet dropped, no SYN‑ACK.

AC4 — Transport auto‑escalation. With plain WG UDP blocked (nft rule), the client escalates the TransportPolicy ladder to MASQUE/H3 and the tunnel stays up. Evidence: StatusReport.transport == "masque-h3", tshark shows HTTP/3 (no WG signature), reachability preserved [04_P0 §5].

AC5 — Live policy reconfig. A Console/CLI policy edit reconfigures all affected devices in < 1 s with zero process restarts. Evidence: helix_reconcile_seconds p99 < 1 s histogram + Console live‑event log.

AC6 — Fast revoke. Revoking a device removes its access in < 1 s (peer dropped from every map + kernel WG peer removed at edge + cert revoked). Evidence: revoke→edge‑enforcement timing capture.

AC7 — Kill‑switch + DNS‑leak. On tunnel drop, no plaintext egress and no DNS leak occur (core state machine drives the firewall). Evidence: host‑side pcap during forced drop shows zero leaked packets (§04, §11.4.107 liveness).

AC8 — No‑logging as code. No durable connection/traffic/packet table exists; the CI schema‑lint fails the build if one appears. Evidence: schemalint green + paired §1.1 mutation (connections table → FAIL) [02 §2.4].

AC9 — Three apps drive it. Access (iOS/Android/Linux), Connector daemon, and Console (web) each exercise AC1–AC7 through generated clients (no hand‑written API code). Evidence: per‑app UX recordings (§11.4.159).

### SLOs (measured, alert‑on‑breach)

| ID | SLO | Target | Item that wires the metric |
| --- | --- | --- | --- |
| SLO1 | event → delta‑on‑wire | p99 < 1 s | HVPN-P1-073 |
| SLO2 | enroll → first NetworkMap | < 2 s | HVPN-P1-031 |
| SLO3 | revoke → edge enforcement | < 1 s | HVPN-P1-033 |
| SLO4 | coordinator memory @ 10k streams | bounded, no leak / 24 h soak | HVPN-P1-074 |

## 2.1 Enroll → reach → revoke (the AC1/AC2/AC6/SLO2/SLO3 evidence sequence)

The single sequence that produces the captured evidence for AC1 (self-host), AC2 (authorized reach), AC6 (revoke <1s), SLO2 (enroll→map<2s) and SLO3 (revoke→edge<1s) — restated from the architecture's ASCII sketch HelixVPN-Architecture-Refined.md §8 as a precise Mermaid sequence diagram, annotated with the implementing work-items:

Implementing items: HVPN-P1-031/032/040/070..073/080..083/090/093/100..102/033. Proving items: HVPN-P1-140 (E2E rig), HVPN-P1-141 (SLO histograms), HVPN-P1-144 (Challenge bank + vision-verified recording).

## 2.2 Phase-gate-failure / rollback protocol

If the Phase‑1 exit gate (all 9 ACs + 4 SLOs, §21) is not met on the planned schedule, the response is scoped by which criterion is red, never a blanket timeline extension (§11.4.42 iteration discipline):

| Failure class | Response | Cross-reference |
| --- | --- | --- |
| A single AC/SLO red, root cause isolated to one epic (e.g. AC5 SLO1 breach in the coordinator fan-out) | Fix-forward inside the owning epic; re-run only the risk-ordered set (§11.4.132) touching that epic + the full DoD sweep before re-declaring green — never spot-validate just the touched item (§11.4.130). | HVPN-P1-145 (release-gate sweep) |
| A Phase‑0 gate (G1–G6, §5) regresses under Phase‑1 load (e.g. G3 iOS memory headroom erodes once the reconciler + kill-switch are added) | Re-open the corresponding decision D2/D1/D5 per v00-meta/decision-register.md §6 reversal criteria — this is a re-open, not a Phase‑1 bug, and follows the same reopen-attribution discipline (§11.4.34) as any other regression. | v00-meta/decision-register.md §6 |
| Scope genuinely cannot close in the planned window (e.g. E12 platform shim effort blew past estimate) | Defer the lowest-priority DoD-adjacent item (never a numbered AC/SLO itself — those are the fixed exit bar) to a tracked Phase‑1.1 follow-up; the release does not tag until all 9 ACs + 4 SLOs are green (§11.4.40 full-suite retest is the gate, not a target date). | §22 effort roll-up (identifies the lowest-priority non-critical-path item to defer) |
| A huge-blocker discovered during Phase‑1 release validation (core capability broken, regression reaching multiple epics) | Execute the full §11.4.129 huge-blocker protocol: STOP all testing → fix all discovered issues → process the last recorded session's evidence → author new tests of every required type → rebuild → reflash → restart (not resume) full validation from the last tag. | §11.4.129 |

No phase-gate failure is silently absorbed into "ship anyway" — the DoD (§2) is the fixed floor; only the path to green (fix-forward / decision-reopen / scope-defer / huge-blocker-restart) is chosen based on the failure class.

## 3. Workable‑item schema (§11.4.93 DB‑ready)

Every leaf in §§5–20 maps 1:1 to a row in the git‑tracked SQLite single source of truth (docs/.workable_items.db, §11.4.93/.95). Loader contract: a deterministic Go/SQL importer parses this Markdown's leaf blocks and upserts by atm_id (here HVPN-P1-NNN[.k]). The DDL the rows must satisfy:

-- docs/.workable_items.db — Phase-1 WBS projection (subset; full schema in 02/§11.4.93)
CREATE TABLE IF NOT EXISTS items (
  atm_id        TEXT PRIMARY KEY,                  -- 'HVPN-P1-021'
  parent_id     TEXT REFERENCES items(atm_id),     -- epic or parent task ('HVPN-P1-E02')
  kind          TEXT NOT NULL CHECK (kind IN ('epic','task','subtask')),
  title         TEXT NOT NULL CHECK (length(title) >= 6),
  description   TEXT NOT NULL CHECK (length(description) >= 40),  -- §11.4.91/.148
  status        TEXT NOT NULL DEFAULT 'Queued'
                CHECK (status IN ('Queued','In progress','Ready for testing',
                                  'In testing','Reopened','Operator-blocked',
                                  'Obsolete (→ Fixed.md)','Completed (→ Fixed.md)')),
  type          TEXT NOT NULL DEFAULT 'Task' CHECK (type IN ('Bug','Feature','Task')),
  severity      TEXT NOT NULL DEFAULT 'normal',
  epic          TEXT NOT NULL,                      -- 'E02'
  module        TEXT NOT NULL,                      -- 'store','coordinator','helix-core',...
  deps          TEXT NOT NULL DEFAULT '[]',         -- JSON array of atm_ids
  deliverable   TEXT NOT NULL,
  acceptance    TEXT NOT NULL,
  effort_days   INTEGER NOT NULL,
  test_types    TEXT NOT NULL,                      -- JSON: ["UNIT","INT","SEC"]  (§11.4.169)
  dod_refs      TEXT NOT NULL DEFAULT '[]',         -- JSON: ["AC3","SLO1"]
  source_refs   TEXT NOT NULL DEFAULT '[]',         -- JSON: ["04_P1 §7","02 §7.2"]
  created_at    TEXT NOT NULL DEFAULT (datetime('now')),
  modified_at   TEXT NOT NULL DEFAULT (datetime('now'))
);
-- per-item test diary (§11.4.149) — PASS row REQUIRES an evidence path:
CREATE TABLE IF NOT EXISTS test_diary (
  id           INTEGER PRIMARY KEY AUTOINCREMENT,
  atm_id       TEXT NOT NULL REFERENCES items(atm_id),
  date_time    TEXT NOT NULL,
  tested_by    TEXT NOT NULL CHECK (tested_by IN ('User','Operator','AI-agent','HelixQA')),
  result       TEXT NOT NULL CHECK (result IN ('PASS','FAIL','SKIP')),
  test_type    TEXT NOT NULL,                       -- one of §11.4.169 vocab
  evidence_path TEXT,                               -- qa-results/<run-id>/...
  observations TEXT NOT NULL,
  CHECK (result <> 'PASS' OR (evidence_path IS NOT NULL AND length(evidence_path) > 0))
);

Example row (one leaf) so the projection is unambiguous:

INSERT INTO items (atm_id,parent_id,kind,title,description,epic,module,deps,
                   deliverable,acceptance,effort_days,test_types,dod_refs,source_refs)
VALUES (
 'HVPN-P1-022','HVPN-P1-E02','task',
 'FORCE RLS + tenant_isolation on all 10 tenant tables',
 'Enable row-level security with a tenant_isolation USING/WITH CHECK policy on every tenant-scoped table and abort startup if the app role can bypass RLS.',
 'E02','store','["HVPN-P1-021"]',
 'migrations/0002_rls.sql; store/rls_guard.go startup check',
 'A query crafted to read tenant B from a tenant-A session returns ZERO rows (captured); startup aborts when role has rolsuper/rolbypassrls.',
 4,'["UNIT","INT","SEC","CHAOS"]','["AC8","AC2","AC3"]','["02 §2.3","04_P1 §2.2"]');

## 4. Epic map + dependency graph

Critical path (red): E02 → E03 → E07 → E09 → E14. The two Phase‑0 make‑or‑break carries (iOS memory G3, edge language G4) are resolved before Phase 1 starts — Phase 1 assumes Rust core + the G4 edge decision are settled [04_P0 §0]. Epics E04/E05/E06 fan out in parallel off E02 (disjoint scope → parallel PWUs, §11.4.58). E13 can start as soon as E07's container shape exists.

## 5. Phase 0 — entry gates (prerequisite)

Phase 0 is not Phase‑1 work but is the entry condition; these items track the gate verdicts that unblock the MVP. If any gate fails, the linked Phase‑1 epic re‑plans (e.g. G3 fail → E12.iOS adopts the §6.4 fallback ladder).

HVPN-P1-E00 — Phase‑0 spike gate certification epic · module: spike

- HVPN-P1-001 — G1 plain‑UDP data‑path gate. S(3) · deps: — · tests: BENCH,E2E

  - Desc: Certify Rust helix-core+boringtun moves real traffic client→gateway→connector LAN over plain UDP at ≥80% bare‑link. Deliverable: bench.sh CSV + ping log [04_P0 §4/§8]. Acceptance: iperf3 through‑tunnel ≥80% bare link; ping to LAN host succeeds. DoD: AC2 (precursor).

- HVPN-P1-002 — G2 MASQUE‑through‑DPI gate. M(5) · deps: HVPN-P1-001 · tests: BENCH,SEC,E2E

  - Desc: Certify the same core tunnels over MASQUE/H3 through a UDP block at ≥50% of plain, surviving 5% loss. Deliverable: tshark capture (classified HTTP/3, no WG signature) + goodput CSV. Acceptance: works with udp dport 51820 drop; ≥50% plain throughput; QUIC loss‑recovery beats UoT strawman. DoD: AC4 (precursor).

- HVPN-P1-003 — G3 iOS NE memory gate (make‑or‑break). M(5) · deps: HVPN-P1-001 · tests: PERF,STRESS,REC

  - Desc: Certify the Rust core in NEPacketTunnelProvider stays under the device memory ceiling with ≥30% headroom over a 30‑min / 1 GB transfer, both transports. Deliverable: Instruments RSS report (peak+steady) [04_P0 §6]. Acceptance: ≥30% headroom plain and MASQUE; else trigger §6.4 fallback decision (§11.4.66).

- HVPN-P1-004 — G4 edge‑language decision. S(3) · deps: HVPN-P1-002 · tests: BENCH,PERF

  - Desc: Decide Rust vs Go for the MASQUE‑terminating edge on benchmark numbers (CPU/Gbps, p99, churn, MASQUE effort). Deliverable: §12 decision‑log row + A/B CSV. Acceptance: recorded decision with evidence; sets E10's language (default lean Rust if within ~10–15%) [04_P0 §7]. Decision: D5.

- HVPN-P1-005 — G5 FFI boundary gate. S(2) · deps: HVPN-P1-001 · tests: UI,E2E

  - Desc: Certify flutter_rust_bridge v2 drives connect/disconnect + live status from Dart. Deliverable: Flutter‑Linux toggle recording. Acceptance: status chip transitions Connecting→Handshaking→Connected(masque,Nms) driven only by the core event stream. Decision: D2 (Rust core).

- HVPN-P1-006 — G6 push‑reconcile gate. XS(1) · deps: HVPN-P1-001 · tests: E2E,FA

  - Desc: Certify the core converges to a static map delta with no restart (the seed of WatchNetworkMap). Deliverable: reconcile demo + map‑delta log. Acceptance: editing map.json brings a new peer up with no process restart; reachability follows.

## 6. E01 — Foundation: repo, proto, codegen, CI floor

HVPN-P1-E01 — Foundation epic · module: repo

- HVPN-P1-010 — Monorepo + submodule layout. M(4) · deps: HVPN-P1-005 · tests: UNIT,FA Desc: Stand up the [SYNTHESIS §6] layout — helix-core/ helix-edge/ helix-go/ helix-proto/ helix-ui/ shims/ deploy/ — each decoupled, reusable, snake_case (§11.4.29), with upstreams/ + install_upstreams per repo (§11.4.36) and the incorporated submodules/ (containers, helix_qa, challenges, docs_chain, security, vision_engine). Deliverable: repo tree + .gitmodules + per‑repo helix-deps.yaml (§11.4.31). Acceptance: install_upstreams configures every declared remote; a fresh clone builds each component skeleton; no active CI workflows present (§11.4.156, CM-NO-ACTIVE-CI green). Tests: FA bootstrap on a throwaway clone.

- HVPN-P1-011 — helix-proto: agent protobuf + buf codegen. M(4) · deps: HVPN-P1-010 · tests: UNIT,FA Desc: Author proto/helix/agent/v1/agent.proto (the Coordinator service: Enroll, WatchNetworkMap, AdvertisePrefixes, ReportStatus, exactly as [02 §4] / [04_P1 §3]) and wire buf generate → Go + Dart + Rust stubs. Deliverable: generated gen/{go,dart,rust}/...; buf.gen.yaml; buf lint/buf breaking config. Acceptance: one source of truth → three generated clients; buf breaking gate fails on an incompatible change; no hand‑written client code exists (§8 [04_P1]).

  - Skeleton (the contract this WBS depends on — full text in [02 §4]):

  - service Coordinator {
  rpc Enroll(EnrollRequest) returns (EnrollResponse);
  rpc WatchNetworkMap(WatchRequest) returns (stream MapUpdate);
  rpc AdvertisePrefixes(AdvertiseRequest) returns (AdvertiseResponse);
  rpc ReportStatus(StatusReport) returns (StatusAck);
}
// MapUpdate.oneof{ NetworkMap snapshot | MapDelta delta | KeepAlive } — peers PRE-FILTERED.

- HVPN-P1-012 — helix-proto: REST OpenAPI + Dart/TS client gen. S(3) · deps: HVPN-P1-011 · tests: UNIT,FA Desc: Define the OpenAPI 3.1 contract for the app‑facing REST surface (/v1/enroll-tokens, /v1/devices, /v1/policies, /v1/networks, /v1/stream) and generate Dart + TS clients. Deliverable: openapi/helix.v1.yaml + generated clients. Acceptance: generated client round‑trips a stub server; drift between spec and handler fails the gen check.

- HVPN-P1-013 — Local dev infra via containers submodule. S(3) · deps: HVPN-P1-010 · tests: INT,FA Desc: On‑demand Postgres+Redis for tests booted only through the containers submodule pkg/boot/pkg/compose/pkg/health (§11.4.76/.161, rootless Podman) — no ad‑hoc docker. Deliverable: internal/testinfra wrapper; make test-infra-up/down. Acceptance: integration tests boot infra on demand; teardown leaves no orphan containers (§11.4.14).

## 7. E02 — Store, schema, RLS, no‑log lint

HVPN-P1-E02 — Store + RLS + no‑log lint (the truth floor) epic · module: store Risk‑first (§11.4.132): this epic is the irreversible correctness floor; it ships before any feature reads/writes data.

- HVPN-P1-020 — Migrations, enums, DB roles. M(4) · deps: HVPN-P1-013 · tests: UNIT,INT Desc: Author the full DDL from [02 §2.2] / [04_P1 §2.1] via goose — tenants users devices connectors advertised_prefixes groups group_members policies overlay_pools device_certs audit_events + enums (user_role, device_kind); create three roles helix_owner (DDL), helix_app (non‑super, non‑bypass — runtime), helix_sys (system tasks). Deliverable: migrations/0001_core.sql..; sqlc.yaml. Acceptance: migrations apply+rollback clean on a fresh PG; \dt matches the spec; no connection/traffic table present.

- HVPN-P1-021 — sqlc typed queries + store.WithTenant. M(4) · deps: HVPN-P1-020 · tests: UNIT,INT Desc: Compile‑time‑checked queries via sqlc; WithTenant(ctx,tid,fn) runs each request inside a tx that SET LOCAL app.tenant_id (tx‑scoped, can't leak across the pool) plus WithSystem for cross‑tenant system tasks. Deliverable: internal/store/*.go, generated Queries. Acceptance: a query that forgets a WHERE tenant_id still returns only the active tenant's rows (proven by INT test).

- HVPN-P1-022 — FORCE RLS + tenant_isolation policies. M(4) · deps: HVPN-P1-021 · tests: UNIT,INT,SEC,CHAOS · DoD: AC8,AC2,AC3 Desc: ENABLE+FORCE ROW LEVEL SECURITY and a tenant_isolation USING/WITH CHECK (tenant_id = current_setting('app.tenant_id')::uuid) on all 10 tenant tables; a startup guard aborts if helix_app has rolsuper/rolbypassrls. Deliverable: migrations/0002_rls.sql; store/rls_guard.go. Acceptance: SEC test — a crafted cross‑tenant read returns zero rows (captured); startup aborts under a super role. CHAOS — connection drop mid‑tx rolls back, no leak.

- ALTER TABLE devices ENABLE ROW LEVEL SECURITY;
ALTER TABLE devices FORCE ROW LEVEL SECURITY;
CREATE POLICY tenant_isolation ON devices
  USING (tenant_id = current_setting('app.tenant_id')::uuid)
  WITH CHECK (tenant_id = current_setting('app.tenant_id')::uuid);
-- repeat for users, connectors, advertised_prefixes, groups, group_members,
--            policies, overlay_pools, device_certs, audit_events

- HVPN-P1-023 — No‑logging CI schema‑lint + mutation. S(3) · deps: HVPN-P1-020 · tests: UNIT,SEC · DoD: AC8 Desc: tools/schemalint fails the build if a durable table named/scoped like a connection log appears (connections|flows|traffic|packets, or any table carrying both a src/dst and a bytes/ts outside audit_events) [02 §2.4]. Deliverable: tools/schemalint/main.go + pre‑build gate. Acceptance: green on the real schema; paired §1.1 mutation — inject a connections(src,dst,bytes,ts) table → lint FAILs (captured). This is the mechanical enforcement of the privacy promise.

## 8. E03 — Identity, enrollment, PKI

HVPN-P1-E03 — Identity / Enrollment / PKI epic · module: identity,pki Risk‑first: revoke‑<1 s and key‑never‑leaves are security‑critical (§04).

- HVPN-P1-030 — Dual identity: OIDC + anonymous device tokens. M(5) · deps: HVPN-P1-022 · tests: UNIT,INT,SEC Desc: Managed mode (tenant admins log in via any OIDC IdP — Keycloak/Authentik) and anonymous mode (mint device enroll‑tokens with no email/SSO — the Mullvad "account number, no PII" posture) [04_P1 §6.1]. Deliverable: internal/identity/; token mint/store‑hashed/consume‑atomic. Acceptance: an anonymous device enrolls with zero PII persisted; an OIDC user maps to a tenant/role; tokens are single‑use and short‑lived (consume is atomic under concurrency — SEC).

- HVPN-P1-031 — Enroll RPC (device key never leaves). M(5) · deps: HVPN-P1-030,HVPN-P1-040,HVPN-P1-032 · tests: UNIT,INT,SEC,E2E · DoD: AC1,AC2; SLO2 Desc: Implement Coordinator.Enroll: verify token → IPAM‑allocate overlay IP → issue short‑lived device cert → persist device row (only the WG public key) → emit device.enrolled [04_P1 §6.2]. Deliverable: enroll handler + flow test. Acceptance: device generates its WG keypair locally; the control plane never receives a private key (SEC asserts absence in logs+DB); enroll → first NetworkMap < 2 s (SLO2, captured).

- HVPN-P1-032 — PKI: device‑cert issuance + tenant CA. M(4) · deps: HVPN-P1-022 · tests: UNIT,INT,SEC Desc: internal/pki issues short‑lived (24 h) mTLS device certs against a per‑tenant CA; the CA root is the one true secret (KMS/offline backup) [04_P1 §6.3, §04]. Deliverable: pki.Issue/Rotate/Revoke; cert store. Acceptance: a cert authenticates the WatchNetworkMap channel; CA private key never appears in any app log (secret‑leak audit, §11.4.10.A).

- HVPN-P1-033 — Cert rotation + revoke‑<1 s. M(4) · deps: HVPN-P1-032,HVPN-P1-070 · tests: UNIT,INT,SEC,PERF · DoD: AC6; SLO3 Desc: Auto‑rotate before expiry over the existing channel; device.revoke drops the WG peer from every relevant map + enforces at the edge (kernel WG peer removed) + marks cert revoked, all within the convergence SLO. Deliverable: rotation scheduler + revoke path. Acceptance: revoke → edge enforcement < 1 s (SLO3, captured timing); a revoked cert is rejected immediately (SEC).

## 9. E04 — IPAM (D4)

HVPN-P1-E04 — Overlay IPAM + subnet‑collision (D4) epic · module: ipam

- HVPN-P1-040 — ULA /48 provisioning + AllocOverlayIP. M(4) · deps: HVPN-P1-022 · tests: UNIT,INT,STRESS Desc: On tenant create, provision an IPv6 ULA /48 (fd7a:helix:<rand>::/48, ::1 = gateway); AllocOverlayIP hands out the next host deterministically + concurrency‑safe [02 §3.2]. Decision D4: IPv6 ULA /48 per tenant resolves RFC1918 collisions across N joined LANs (recommended over CGNAT‑100.64 1:1 NAT) [SYNTHESIS §3 D4, 04_ARCH §3.4]. Deliverable: internal/ipam/. Acceptance: 1000 concurrent allocations yield no duplicate/gap (STRESS, captured); allocation is restart‑stable (re‑hydrates next_host).

- HVPN-P1-041 — 4via6 for colliding IPv4 LANs. M(5) · deps: HVPN-P1-040,HVPN-P1-060 · tests: UNIT,INT,E2E Desc: Map each connector site to a stable site‑id and emit Tailscale‑style 4via6 routes so a client may reach two connectors that both advertise 192.168.50.0/24 without collision. Deliverable: site‑id allocator + 4via6 route synthesis feeding Peer.allowed_ips. Acceptance: E2E — one client reaches the same IPv4 CIDR served by two different connectors, disambiguated by site (captured curl to each).

## 10. E05 — Event backbone (D3)

HVPN-P1-E05 — Event backbone: Redis Streams (D3) epic · module: events

- HVPN-P1-050 — events.Bus Redis Streams impl + envelope. M(4) · deps: HVPN-P1-013 · tests: UNIT,INT,CHAOS Desc: Bus‑agnostic events.Bus interface over Redis Streams: XADD produce, XReadGroup durable consumer groups, XACK, the §5.2 envelope (id,type,tenant_id,ts,actor,payload,trace_id). Decision D3: Redis Streams for MVP, NATS JetStream is the Phase‑2 swap behind the same interface [SYNTHESIS §3 D3, 04_P1 §5]. Deliverable: internal/events/. Acceptance: at‑least‑once delivery with idempotent reactions; a replayed event is harmless (INT); a consumer crash mid‑handle re‑delivers on restart (CHAOS).

- HVPN-P1-051 — DLQ sweeper (XAUTOCLAIM) + metric. S(3) · deps: HVPN-P1-050 · tests: UNIT,INT,CHAOS Desc: Reclaim stuck pending entries with XAUTOCLAIM, route exhausted‑retry entries to a dead‑letter, expose helix_events_dlq_total. Deliverable: sweeper goroutine + metric. Acceptance: a poisoned event lands in DLQ after N retries (captured), the metric increments, the live stream keeps flowing (CHAOS).

- HVPN-P1-052 — Event taxonomy producers. S(3) · deps: HVPN-P1-050 · tests: UNIT,INT Desc: Wire the concrete taxonomy from [04_P1 §5.3] — device.enrolled/online/offline/revoked, connector.attached, connector.prefixes.changed, route.conflict.detected, policy.updated/compiled, gateway.failover — emitted by identity/registry/policy/edge. Deliverable: typed event constructors. Acceptance: each producer emits a well‑formed envelope on its trigger (INT, captured stream read).

## 11. E06 — Policy model & compiler

HVPN-P1-E06 — Policy model + compiler epic · module: policy

- HVPN-P1-060 — Spec parse + group/host resolution. M(5) · deps: HVPN-P1-022 · tests: UNIT,INT,SEC Desc: Parse the Tailscale‑ACL‑flavored policies.spec jsonb (groups, hosts, acls, exitNodes) [04_P1 §7.1]; resolve group:* → device‑id sets (via users + group_members) and host → CIDRs, cross‑checking against advertised_prefixes (emit route.conflict.detected on ambiguity). Deliverable: internal/policy/parse.go,resolve.go. Acceptance: unknown group/host rejected; an ACL granting a revoked device rejected (SEC).

- HVPN-P1-061 — Two‑artifact compiler (AllowedIPs + verdict map). L(7) · deps: HVPN-P1-060 · tests: UNIT,SEC,PERF · DoD: AC2,AC3 Desc: Pure, deterministic, default‑deny compile(tenant,spec)→{visible,allowedIPs,exitNodes} [04_P1 §7.2] producing two artefacts: coarse WG AllowedIPs (per‑peer CIDR, data path) and a port‑level verdict map (nftables/eBPF at the edge, since WG AllowedIPs is CIDR‑only). Output is exactly what coordinator.buildMap consumes; peers are need‑to‑know filtered. Deliverable: policy/compile.go + golden‑table tests (spec → expected visible/allowedIPs). Acceptance: same spec ⇒ byte‑identical output (determinism property test); a contractor granted only warehouse-cams:554,80 cannot reach port 22 (verdict‑map SEC test); compile of a 1k‑device tenant < 100 ms (PERF).

- HVPN-P1-062 — Dry‑run fail‑closed validation + atomic activate/rollback. M(4) · deps: HVPN-P1-061 · tests: UNIT,INT,SEC · DoD: AC5 Desc: policy.update runs the compiler in dry‑run first; reject on unknown ref, a dst CIDR not covered by any advertised prefix, or a grant to a revoked device. Only a clean compile bumps policies.version, persists the compiled artefact, and emits policy.compiled; a prior version re‑activates instantly (rollback) [04_P1 §7.3/§7.4]. Deliverable: validation + version activation. Acceptance: a bad policy never reaches the active version (fail‑closed, captured); rollback restores the prior compiled set atomically (INT).

## 12. E07 — Coordinator & WatchNetworkMap

HVPN-P1-E07 — Coordinator + WatchNetworkMap epic · module: coordinator Critical path; the < 1 s convergence promise lives here.

- HVPN-P1-070 — In‑memory per‑tenant topology graph. M(5) · deps: HVPN-P1-052,HVPN-P1-061,HVPN-P1-032 · tests: UNIT,INT,SCALE Desc: Hydrate a per‑tenant graph (devices, connectors, prefixes, groups, compiled policy) from Postgres on boot and keep it fresh by consuming events; the coordinator owns no durable tables [04_P1 §4.1]. Deliverable: internal/coordinator/graph.go. Acceptance: graph reconstructable from PG + events alone (proves Phase‑2 stateless‑coordinator seam); applying an event mutates only the affected subgraph (INT).

- HVPN-P1-071 — buildMap(node) per‑node map computation. M(4) · deps: HVPN-P1-070 · tests: UNIT,SEC · DoD: AC2,AC3 Desc: buildMap returns NetworkMap{self,gateway,peers,dns,transport} where peers = policy.PeersVisibleTo(node) (need‑to‑know) each with compiled AllowedIPs; relayEndpoint always routes via the gateway in MVP (hub‑and‑spoke, identical to the proven Phase‑0 slice) [04_P1 §4.2]. Deliverable: coordinator/buildmap.go. Acceptance: a node never appears in another node's map unless policy grants it (SEC — the privacy invariant, captured).

- HVPN-P1-072 — WatchNetworkMap stream loop. L(7) · deps: HVPN-P1-071,HVPN-P1-080 · tests: UNIT,INT,E2E,CHAOS · DoD: AC5 Desc: Implement the streaming RPC: authenticate device by mTLS cert → send snapshot (or resume from known_version) → delta loop on the event subscription + keepalive ticker, with a bounded per‑stream send queue (slow‑consumer protection) [04_P1 §4.3]. Deliverable: coordinator/watch.go. Acceptance: reconnect with known_version=N resumes from deltas (no full resync, captured); a slow/stalled consumer is shed without blocking others (CHAOS).

- func (c *Coordinator) WatchNetworkMap(ctx context.Context,
    req *connect.Request[agentv1.WatchRequest],
    stream *connect.ServerStream[agentv1.MapUpdate]) error {
    dev := authDevice(ctx)                     // mTLS device cert (HVPN-P1-032)
    sub := c.subscribe(dev.TenantID, dev.ID); defer sub.Close()
    _ = stream.Send(snapshotOrResume(c.buildMap(dev), req.Msg.KnownVersion))
    ka := time.NewTicker(20 * time.Second); defer ka.Stop()
    for {
      select {
      case <-ctx.Done(): return ctx.Err()
      case d := <-sub.C: if err := stream.Send(deltaUpdate(d)); err != nil { return err }
      case <-ka.C:       _ = stream.Send(keepAlive())
      }
    }
}

- HVPN-P1-073 — Minimal‑affected‑set fan‑out + reconcile metric. M(5) · deps: HVPN-P1-072 · tests: UNIT,INT,PERF · DoD: AC5; SLO1 Desc: On each event compute the minimal affected open‑stream set (never broadcast a full resync on a small change) and enqueue per‑stream deltas; instrument helix_reconcile_seconds from event‑arrival to delta‑on‑wire [04_P1 §4.4]. Deliverable: fan‑out + histogram. Acceptance: event → delta‑on‑wire p99 < 1 s (SLO1, captured histogram); a 1‑device policy change touches only the affected streams (INT count assertion).

- HVPN-P1-074 — 24 h soak / 10k‑stream memory bound. M(5) · deps: HVPN-P1-073 · tests: SCALE,STRESS,PERF · DoD: SLO4 Desc: Drive N=10k simulated agents holding streams while flapping policies; assert convergence SLO holds and coordinator RSS is bounded with no leak over 24 h. Deliverable: test/soak/ harness + RSS time‑series. Acceptance: SLO1 maintained under load; coordinator memory bounded, no growth over 24 h (SLO4, captured graph).

## 13. E08 — API surface + authz

HVPN-P1-E08 — API: Gin REST + Connect + WS/SSE + authz epic · module: api

- HVPN-P1-080 — Connect handlers mounted on the Gin listener + mTLS resolver. M(4) · deps: HVPN-P1-011,HVPN-P1-032 · tests: UNIT,INT,SEC Desc: One multiplexed server: Connect handlers (HTTP/2 native agents, downgrade for browsers) mounted alongside Gin REST; authDevice(ctx) resolves the device identity from its mTLS cert [04_P1 §8]. Deliverable: internal/api/server.go, authz_device.go. Acceptance: a native agent and a gRPC‑Web caller both reach Coordinator; an unauthenticated agent RPC is rejected (SEC).

- HVPN-P1-081 — REST routes + OpenAPI + RBAC. M(5) · deps: HVPN-P1-080,HVPN-P1-012 · tests: UNIT,INT,SEC Desc: Gin routes (/v1/enroll-tokens, /v1/devices, /v1/policies, /v1/networks, /v1/audit) behind OIDC/session‑or‑API‑token + RBAC (admin/operator/member), with RLS as the backstop. Deliverable: route handlers + RBAC middleware. Acceptance: a member token cannot mint enroll‑tokens (403, SEC); RLS prevents cross‑tenant reads even if RBAC is bypassed (defense‑in‑depth INT).

- HVPN-P1-082 — GET /v1/stream live WS/SSE fan‑out. S(3) · deps: HVPN-P1-081,HVPN-P1-052 · tests: UNIT,INT,E2E Desc: Stream control‑plane events (device.online, route.changed, handshake.failing, policy v N active) to the Console over WebSocket/SSE [04_P1 §8]. Deliverable: api/stream.go. Acceptance: a policy apply surfaces a live "policy v N active; K devices updated" event to a connected Console within the convergence window (E2E, captured).

- HVPN-P1-083 — AdvertisePrefixes + ReportStatus RPCs. S(3) · deps: HVPN-P1-080,HVPN-P1-052 · tests: UNIT,INT,SEC Desc: AdvertisePrefixes accepts connector CIDRs (also settable via Console) emitting connector.prefixes.changed; ReportStatus carries presence + current transport + rtt only (deliberately no bytes/flows/destinations — the no‑logging invariant on the wire). Deliverable: both handlers. Acceptance: a status report persists no traffic data (SEC asserts the message has no byte/flow fields); advertised prefixes flow into the coordinator graph (INT).

## 14. E09 — helix‑core (Rust client/connector)

HVPN-P1-E09 — helix‑core: Rust client/connector epic · module: helix-core The shared client/connector/edge crate; the durable evolution of the Phase‑0 interfaces.

- HVPN-P1-090 — Transport trait + plain‑UDP + MASQUE impls. L(8) · deps: HVPN-P1-002 · tests: UNIT,BENCH,SEC,E2E · DoD: AC4 Desc: Harden the Phase‑0 Transport trait (send/recv/kind/effective_mtu, unreliable datagrams) + plain_udp + masque (quinn + h3 + hand‑rolled CONNECT‑UDP / HTTP‑Datagram framing per RFC 9298/9297/9221) into the production crate helix-transport [04_P0 §4.2/§5, 03 §transport]. Decision D1: MASQUE/QUIC primary obfuscating transport (true Mullvad parity, single Rust impl) — surfaced against the Hysteria2 alternative [SYNTHESIS §3 D1]. Deliverable: crates/helix-transport/. Acceptance: MASQUE flow classifies as HTTP/3 with no WG signature (tshark, SEC); ≥50% plain throughput (BENCH); same trait drives all three consumers byte‑for‑byte.

- HVPN-P1-091 — helix-wg boringtun wrapper. M(5) · deps: HVPN-P1-090 · tests: UNIT,E2E,STRESS Desc: Production wrapper around boringtun Tunn (handshake, encrypt/decrypt, timer tick, the four WgVerdict outputs) — pure‑userspace WG identical on Linux/Android/iOS [04_P0 §4.4]. Deliverable: crates/helix-wg/. Acceptance: sustained 1 GB transfer with no handshake stall (STRESS); rekey at the 2‑min boundary works (captured).

- HVPN-P1-092 — Orchestrator + network‑map reconciler. L(7) · deps: HVPN-P1-091,HVPN-P1-072 · tests: UNIT,E2E,FA,CHAOS · DoD: AC5 Desc: The three‑loop orchestrator (tun→wg→transport, transport→wg→tun, timer) + a reconciler that consumes streamed MapUpdate (snapshot/delta) and converges peers/AllowedIPs/transport without restart; client vs connector routing posture via mode [04_P0 §4.5, 04_P1 §3]. Deliverable: crates/helix-core/. Acceptance: a streamed delta adds/removes a peer with no reconnect of unrelated state (FA); a mid‑stream coordinator restart re‑syncs from known_version (CHAOS).

- HVPN-P1-093 — Auto‑escalation ladder. M(5) · deps: HVPN-P1-090,HVPN-P1-092 · tests: UNIT,E2E,SEC · DoD: AC4 Desc: Walk TransportPolicy.order (["plain-udp","lwo","masque-h3"]) on handshake failure, honoring allow_user_override; emit transport in ReportStatus. Deliverable: ladder state machine. Acceptance: with plain WG blocked the client escalates to MASQUE and stays up (E2E, captured transport=="masque-h3"); ladder is deterministic across N runs (§11.4.50).

- HVPN-P1-094 — Kill‑switch + DNS‑leak protection. L(7) · deps: HVPN-P1-092 · tests: UNIT,E2E,SEC,CHAOS · DoD: AC7 Desc: A core state machine drives the platform firewall so that on tunnel Down/Reconnecting no plaintext egress and no DNS leak occur; DNS is pinned to the overlay resolver while up [04_P1 §11.2, §04]. Deliverable: kill‑switch module + per‑OS firewall hooks (called by shims). Acceptance: host‑side pcap during a forced drop shows zero leaked packets and zero plaintext DNS (SEC, captured); state survives an abrupt interface flap (CHAOS).

- HVPN-P1-095 — helix-ffi (flutter_rust_bridge v2) surface. M(4) · deps: HVPN-P1-092 · tests: UNIT,UI,FA Desc: The tiny stable FFI: start(ClientConfig), stop(), status_stream(StreamSink<TunnelStatus>) mirroring the core broadcast channel (Connecting|Handshaking|Connected{transport,rtt}|Reconnecting|Down{reason}) [04_P0 §9]. Deliverable: crates/helix-ffi/ + generated Dart bindings. Acceptance: Dart drives connect/disconnect and renders live status from the stream alone (UI golden + FA re‑run ×3).

## 15. E10 — helix‑edge (data plane)

HVPN-P1-E10 — helix‑edge data plane epic · module: helix-edge Language fixed by Phase‑0 G4 (HVPN-P1-004); default lean Rust sharing helix-transport [04_P0 §7].

- HVPN-P1-100 — MASQUE termination on :443/udp + masquerade. L(8) · deps: HVPN-P1-090,HVPN-P1-004 · tests: UNIT,BENCH,SEC,E2E · DoD: AC4 Desc: Terminate MASQUE/H3, extract HTTP Datagrams → WG → kernel WG; serve a believable decoy site to anything that isn't a valid CONNECT‑UDP flow (native camouflage) [04_P0 §5.4, 01]. Deliverable: helix-edge/ listener. Acceptance: a scanner hitting :443 sees a plain website; a valid client tunnels through (SEC + E2E, captured); CPU/Gbps within the G4 budget (BENCH).

- HVPN-P1-101 — Kernel‑WG peer programming + relay (hub‑and‑spoke). M(5) · deps: HVPN-P1-100,HVPN-P1-072 · tests: UNIT,INT,E2E · DoD: AC2 Desc: Program kernel WG peers from the coordinator's map and relay peer↔peer traffic via the gateway (MVP hub‑and‑spoke; direct P2P is Phase 2) [04_P1 §4.2]. Deliverable: edge↔coordinator sync + WG config apply. Acceptance: client reaches an authorized connector LAN host through the relay (E2E, captured curl).

- HVPN-P1-102 — Edge verdict‑map enforcement (nftables/eBPF) + revoke drop. M(5) · deps: HVPN-P1-061,HVPN-P1-101,HVPN-P1-033 · tests: UNIT,INT,SEC,PERF · DoD: AC3,AC6; SLO3 Desc: Apply the policy compiler's port‑level verdict map at the edge (the port granularity WG AllowedIPs lacks) and drop a revoked device's sessions on device.revoked [04_P1 §7.2]. Deliverable: nftables/eBPF programmer. Acceptance: an unauthorized port is dropped (AC3 SEC, captured); revoke removes the kernel peer < 1 s (SLO3, captured); enforcement adds negligible p99 (PERF).

- HVPN-P1-103 — Edge hardening posture. S(3) · deps: HVPN-P1-100 · tests: SEC,CHAOS Desc: Rootless Podman, read‑only rootfs, seccomp, NET_ADMIN‑only, no SSH in the edge container, fail‑static (Go/control never in the packet path) [SYNTHESIS §7, §04]. Deliverable: edge container manifest + seccomp profile. Acceptance: the container runs unprivileged except NET_ADMIN; killing the control plane does not drop established data‑plane tunnels (fail‑static CHAOS, captured).

## 16. E11 — helix‑ui (Flutter) + design system

HVPN-P1-E11 — helix‑ui: Flutter design system + 3 flavors epic · module: helix-ui All UI under OpenDesign tokens (§11.4.162) — light+dark, no ad‑hoc CSS; Riverpod state = pure function of the core status stream [03, 04_ARCH §5].

- HVPN-P1-110 — helix_design system (OpenDesign tokens, Material 3). M(5) · deps: HVPN-P1-010 · tests: UNIT,UI,REC Desc: Brand‑tokenized design system (connection‑state palette, signature components: ConnectButton, StatusChip, ExitPicker, ShieldIndicator, AdaptiveScaffold) with light+dark variants via OpenDesign (§11.4.162), no overlapping labels. Deliverable: helix-ui/packages/helix_design/. Acceptance: visual‑regression goldens pass for every component in both themes (UI); a window‑scoped MP4 shows the palette reacting to connection state (REC, vision‑verified §11.4.159).

- HVPN-P1-111 — Shared shell runHelixApp(flavor,…) + Riverpod core‑status binding. M(4) · deps: HVPN-P1-110,HVPN-P1-095 · tests: UNIT,UI,FA Desc: One tree → three flavors via runHelixApp(flavor, home, capabilities) (Access / Connector / Console), with Riverpod providers derived purely from the helix-ffi status stream [03]. Deliverable: helix-ui/app/. Acceptance: the same widget tree renders all three flavors; UI state is a deterministic function of a replayed status stream (FA).

- HVPN-P1-112 — Access app screens (enroll → connect → reach). L(7) · deps: HVPN-P1-111,HVPN-P1-012 · tests: UI,UX,E2E,REC · DoD: AC9 Desc: End‑user flow: paste/scan enroll token → connect → ExitPicker / authorized‑network list → live status. Deliverable: Access flavor screens. Acceptance: a real enroll→connect→reach‑LAN journey recorded as a window‑scoped MP4 with a vision verdict that the authorized host loaded (UX/REC, §11.4.159/.143); golden tests for each screen (UI).

- HVPN-P1-113 — Console (web) admin screens. L(7) · deps: HVPN-P1-111,HVPN-P1-082 · tests: UI,UX,E2E,SEC,REC · DoD: AC5,AC9 Desc: The Web‑only flavor (no core_ffi): devices, enroll‑tokens, policy editor (validate→activate→rollback), live event feed via /v1/stream. Deliverable: Console flavor. Acceptance: a policy edit in the Console reflects on devices < 1 s with a live "policy v N active" feed (E2E/REC, AC5); RBAC hides admin actions from member (SEC).

- HVPN-P1-114 — Connector daemon UI/headless control. M(4) · deps: HVPN-P1-111,HVPN-P1-083 · tests: UI,E2E,REC · DoD: AC9 Desc: The Connector flavor: enroll, advertise CIDRs, show advertised prefixes + reachability/health (runs headless on a host with a thin status UI). Deliverable: Connector flavor + daemon mode. Acceptance: a connector advertises a LAN and its prefixes appear in the Console + a client's map (E2E, captured).

## 17. E12 — Platform tunnel shims (iOS/Android/Linux)

HVPN-P1-E12 — Platform TunnelPlatform shims epic · module: shims MVP platforms only: iOS, Android, Linux (Windows/macOS = Phase 2; HarmonyOS/Aurora = Phase 3). The shim is the only platform‑specific code [SYNTHESIS §5].

- HVPN-P1-120 — Linux tun shim (Rust‑native). S(3) · deps: HVPN-P1-092 · tests: E2E,FA · DoD: AC1,AC2 Desc: Linux core drives the TUN directly (kernel WG or userspace); the reference platform for the netns E2E rig. Deliverable: shims/linux/. Acceptance: the Access Linux build runs the full enroll→connect→reach journey on the netns rig (E2E).

- HVPN-P1-121 — Android VpnService + JNI shim. M(5) · deps: HVPN-P1-092,HVPN-P1-094 · tests: E2E,UX,REC,SEC · DoD: AC7,AC9 Desc: VpnService owns the TUN; JNI loads helix-core.so; the kill‑switch maps to VpnService always‑on/lockdown semantics. Deliverable: shims/android/ (Kotlin+JNI). Acceptance: tunnel up on a real phone (REC device recording); kill‑switch blocks plaintext on drop (SEC, captured).

- HVPN-P1-122 — iOS NEPacketTunnelProvider shim (within G3 budget). L(8) · deps: HVPN-P1-003,HVPN-P1-092,HVPN-P1-094 · tests: E2E,UX,REC,PERF,SEC · DoD: AC7,AC9 Desc: NEPacketTunnelProvider (Swift) configures NEPacketTunnelNetworkSettings and pumps packetFlow ↔ the Rust core; honor the G3 memory ceiling (apply §6.4 fallbacks only if G3 demanded them) [04_P0 §6]. Deliverable: shims/apple/ios/. Acceptance: tunnel up on a real device within the memory ceiling over a sustained transfer (PERF/REC, captured Instruments RSS); kill‑switch + DNS‑leak hold (SEC).

## 18. E13 — Deploy: helixvpnctl + Podman quadlets + containers submodule

HVPN-P1-E13 — Deploy & operations epic · module: deploy

- HVPN-P1-130 — helixvpnctl bootstrap + ops CLI (Cobra). M(5) · deps: HVPN-P1-020,HVPN-P1-130_dep · tests: UNIT,FA,E2E · DoD: AC1 Desc: The ops CLI replacing bash installers: init (generates tenant, admin, CA root, overlay /48, PG/Redis creds, gateway WG keys, quadlets), gateway keys, enroll-token, policy apply, device revoke [04_P1 §9.1]. Deliverable: cmd/helixvpnctl/. Acceptance: helixvpnctl init on a fresh host produces a runnable deploy (FA, captured); policy apply ./policy.jsonc validates + activates (E2E).

- helixvpnctl init --domain gw.example.com --data-dir /var/lib/helixvpn
helixvpnctl gateway keys
helixvpnctl enroll-token --kind connector --site warehouse   # prints token / QR
helixvpnctl policy apply ./policy.jsonc                        # dry-run compile → activate
helixvpnctl device revoke <id>

- HVPN-P1-131 — Podman quadlets (rootless, systemd‑managed). M(4) · deps: HVPN-P1-130,HVPN-P1-103 · tests: INT,FA,SEC · DoD: AC1 Desc: Render the pod quadlets (helixd, helix-edge, postgres, redis) — rootless, read‑only rootfs, helixd connects to PG as the non‑superuser role so RLS is enforced [04_P1 §9.2, §11.4.161]. Deliverable: deploy/quadlet/*.container, helixvpn.pod. Acceptance: systemctl --user start helixvpn-pod brings the stack up rootless (FA); the app role cannot bypass RLS (SEC).

- # deploy/quadlet/helixd.container  (rootless; read-only rootfs)
[Container]
Image=ghcr.io/helixdevelopment/helixd:1.0
Pod=helixvpn.pod
Environment=DATABASE_URL=postgres://helix_app@localhost/helix   # NON-superuser → RLS enforced
Environment=REDIS_URL=redis://localhost:6379
ReadOnly=true
[Container]  # helix-edge — winner of Phase-0 G4
Image=ghcr.io/helixdevelopment/helix-edge:1.0
Pod=helixvpn.pod
AddCapability=NET_ADMIN     # :443/udp MASQUE + kernel WG; no SSH in this container

- HVPN-P1-132 — On‑demand integration infra via containers submodule. S(3) · deps: HVPN-P1-013,HVPN-P1-131 · tests: INT,FA Desc: Wire the §14 QA harness to boot the full stack on demand through the containers submodule (§11.4.76) so integration/E2E never require a manual podman up. Deliverable: deploy/integration/. Acceptance: the E2E suite boots+tears down the stack itself (FA, captured).

- HVPN-P1-133 — Compose dev‑loop + K8s Phase‑2 shape (reference). S(2) · deps: HVPN-P1-131 · tests: INT Desc: A Docker Compose dev‑loop equivalent (local only) and a stateless‑coordinator Kubernetes manifest as reference proving the Phase‑1 seams permit HA without reshaping [02 §11.2/§11.3]. Deliverable: deploy/compose/dev.yml, deploy/k8s/helixd-deployment.yaml. Acceptance: dev compose boots PG+Redis+helixd locally; the K8s manifest is lint‑valid (not deployed at MVP).

## 19. E14 — QA, SLOs, DoD certification

HVPN-P1-E14 — QA · SLOs · DoD certification epic · module: qa Anti‑bluff capstone: this epic owns the §11.4.40 full‑suite retest, the §11.4.107 recorded evidence, and the §11.4.27 100%‑type coverage that turn the 8 ACs from claims into proofs.

- HVPN-P1-140 — netns + DPI + netem E2E rig (CI‑ready). M(5) · deps: HVPN-P1-101,HVPN-P1-120 · tests: E2E,FA Desc: Promote the Phase‑0 rig to a reproducible, fully‑automated harness now fed by the real control plane: lanA netns service, nft WG‑block for AC4, tc netem loss/delay, make e2e [04_P0 §3]. Deliverable: test/e2e/rig/. Acceptance: make e2e runs the full slice unattended and re‑runs -count=3 identically (FA, §11.4.98).

- HVPN-P1-141 — SLO instrumentation + dashboards. S(3) · deps: HVPN-P1-073,HVPN-P1-074,HVPN-P1-031,HVPN-P1-033 · tests: PERF,FA · DoD: SLO1-4 Desc: Prometheus metrics (helix_reconcile_seconds, enroll/revoke timers, coordinator RSS) + Grafana‑as‑code dashboards + alert rules at the §2 SLO targets. Deliverable: deploy/observability/. Acceptance: all four SLOs measured and asserted in CI thresholds (captured histograms, alert‑on‑breach).

- HVPN-P1-142 — Security test suite (RLS, key‑never‑leaves, mTLS, kill‑switch, leak audit). L(7) · deps: HVPN-P1-022,HVPN-P1-031,HVPN-P1-094,HVPN-P1-102 · tests: SEC,CHAOS,SCALE · DoD: AC3,AC6,AC7,AC8 Desc: Consolidate the security‑critical assertions into one suite driven by the security submodule tooling (§04): cross‑tenant RLS denial, private‑key absence, mTLS rejection of bad certs, kill‑switch/DNS‑leak pcap, revoke timing, secret‑leak repo audit (§11.4.10.A). Deliverable: test/security/. Acceptance: every assertion green with captured evidence; paired §1.1 mutations (drop an RLS policy / weaken kill‑switch) FAIL their gate.

- HVPN-P1-143 — Stress + chaos suite (§11.4.85). M(5) · deps: HVPN-P1-072,HVPN-P1-050,HVPN-P1-092 · tests: STRESS,CHAOS,SCALE Desc: Sustained‑load + concurrency + boundary + failure‑injection across the control plane (Redis kill mid‑event, PG drop mid‑tx, coordinator SIGKILL with open streams, disk‑full) with categorized recovery [§11.4.85]. Deliverable: test/stress_chaos/. Acceptance: every fault recovers to a consistent state with a captured recovery_trace.log; no deadlock/leak under 10× concurrency.

- HVPN-P1-144 — HelixQA Challenge bank + vision‑verified recordings. M(5) · deps: HVPN-P1-112,HVPN-P1-113,HVPN-P1-140 · tests: CHAL,REC,UX · DoD: AC1-AC9 Desc: Author a challenges/helix_qa bank where each Challenge dispatches a real user journey and scores PASS only on captured evidence; every user‑visible AC gets a window‑scoped MP4 run through the §11.4.163 media‑validation pipeline (vision verdict vs SPECIFY‑phase patterns) [§11.4.27/.107/.158/.159/.160]. Deliverable: submodules/challenges/banks/helixvpn.yaml + docs/qa/<run-id>/. Acceptance: the 8‑AC journey set scores PASS with a vision‑confirmed MP4 per AC (no frozen/bluff frame, §11.4.107); a deliberately broken build scores FAIL (analyzer self‑validated golden‑good/bad).

- HVPN-P1-145 — Full‑suite retest + DoD certification gate. M(4) · deps: HVPN-P1-140,HVPN-P1-141,HVPN-P1-142,HVPN-P1-143,HVPN-P1-144 · tests: FA,E2E,CHAL · DoD: AC1-AC9,SLO1-4 Desc: The §11.4.40 release‑gate sweep on a clean baseline (pre‑build + post‑build + on‑device + meta‑mutation + Challenge bank + no‑log lint + CONTINUATION sync), asserting all 8 ACs + 4 SLOs end‑to‑end on a fresh §11.4.108 deploy. Deliverable: scripts/release_gate.sh + the certification report under docs/qa/release/. Acceptance: all of §21 green simultaneously on a from‑zero install; any red blocks the tag.

## 20. E15 — Docs‑chain, workable‑items DB, release

HVPN-P1-E15 — Docs‑chain, items DB, release epic · module: governance

- HVPN-P1-150 — Workable‑items DB projection + docs‑chain sync. M(4) · deps: HVPN-P1-010 · tests: UNIT,INT,FA Desc: Implement the §3 loader: parse this WBS's leaves → upsert items/test_diary in docs/.workable_items.db (git‑tracked, §11.4.95) and register the docs‑chain context so HTML/PDF/DOCX exports + the DB stay in lockstep (§11.4.106/.93/.65/.153). Deliverable: cmd/workable-items/ + .docs_chain/contexts/wbs.yaml. Acceptance: md↔db byte‑identical round‑trip (§11.4.93); a leaf edit re‑syncs exports out‑of‑the‑box; verify is the CI gate.

- HVPN-P1-151 — Release tagging + multi‑upstream publish. S(3) · deps: HVPN-P1-145,HVPN-P1-150 · tests: FA · DoD: AC1-AC9 Desc: Cut the prefixed release tag (<HELIX_RELEASE_PREFIX>-1.0.0-mvp from .env else snake_case root dir, §11.4.151) on the main repo and every owned submodule with the identical prefix, published to all upstreams via merge‑onto‑latest‑main (no force‑push, §11.4.113). Deliverable: the tag set + changelog under docs/changelogs/. Acceptance: git tag -l '<PREFIX>-*' enumerates the whole release across repos; the DoD certification report (HVPN-P1-145) is the tag's evidence; the tag is reachable on every remote.

## 21. DoD ↔ work‑item traceability matrix

Each release gate must trace to at least one implementing item and one proving (test/QA) item. A gate with no green proving item cannot ship (§11.4.123 rock‑solid proof).

| Gate | Implementing items | Proving items |
| --- | --- | --- |
| AC1 self‑host from zero | HVPN-P1-130, 131, 132 | HVPN-P1-144, 145 |
| AC2 authorized reach | HVPN-P1-031, 071, 101, 041 | HVPN-P1-140, 144 |
| AC3 default‑deny | HVPN-P1-061, 071, 102 | HVPN-P1-142, 144 |
| AC4 transport auto‑escalate | HVPN-P1-090, 093, 100 | HVPN-P1-002, 140, 144 |
| AC5 policy edit < 1 s | HVPN-P1-062, 072, 073, 113 | HVPN-P1-141, 144 |
| AC6 revoke < 1 s | HVPN-P1-033, 102 | HVPN-P1-141, 142 |
| AC7 kill‑switch + DNS‑leak | HVPN-P1-094, 121, 122 | HVPN-P1-142, 144 |
| AC8 no durable log | HVPN-P1-020, 023, 083 | HVPN-P1-023 (mutation), 142 |
| AC9 three apps drive it | HVPN-P1-112, 113, 114 | HVPN-P1-144 |
| SLO1 event→delta p99<1s | HVPN-P1-073 | HVPN-P1-141 |
| SLO2 enroll→map <2s | HVPN-P1-031 | HVPN-P1-141 |
| SLO3 revoke→edge <1s | HVPN-P1-033, 102 | HVPN-P1-141, 142 |
| SLO4 coord mem @10k | HVPN-P1-074 | HVPN-P1-141, 143 |

## 22. Effort roll‑up & critical path

Indicative person‑day totals (mid‑point of the T‑shirt range) for sizing, not a commitment — Phase‑0 carries (G3/G4) are excluded as prerequisites.

| Epic | Items | ~Person‑days |
| --- | --- | --- |
| E00 Phase‑0 gates (prereq) | 6 | 19 |
| E01 Foundation | 4 | 14 |
| E02 Store + RLS + lint | 4 | 15 |
| E03 Identity/Enroll/PKI | 4 | 18 |
| E04 IPAM | 2 | 9 |
| E05 Events | 3 | 10 |
| E06 Policy compiler | 3 | 16 |
| E07 Coordinator | 5 | 26 |
| E08 API + authz | 4 | 15 |
| E09 helix‑core (Rust) | 6 | 36 |
| E10 helix‑edge | 4 | 21 |
| E11 helix‑ui (Flutter) | 5 | 27 |
| E12 Platform shims | 3 | 16 |
| E13 Deploy | 4 | 14 |
| E14 QA · SLOs · DoD | 6 | 29 |
| E15 Governance/release | 2 | 7 |
| MVP total (excl. E00) | 59 | ~273 |

Critical path (longest dependency chain to AC certification): E01(010→011) → E02(020→021→022) → E03(032) → E07(070→071→072→073) → E09(092→093/094) → E10(100→101→102) → E14(140→142→144→145) → E15(151). The two parallelizable fan‑outs that keep wall‑clock down: E04/E05/E06 off E02 (disjoint scope → concurrent PWUs §11.4.58), and E11 UI off E08/E09 in parallel with E10/E12. Audio‑style "top priority first" maps here to the security/correctness floor (E02 RLS, E03 revoke, E09 kill‑switch) leading every iteration per §11.4.132.

Open decisions surfaced (not silently resolved), each with a recommendation and the gate that finalizes it: D1 MASQUE/QUIC primary (rec: yes — Mullvad parity, HVPN-P1-090) · D2 Rust core (rec: yes — G3/G5, settled) · D3 Redis Streams MVP → NATS Phase 2 (rec: yes, HVPN-P1-050) · D4 IPv6 ULA /48

- 4via6 (rec: yes — HVPN-P1-040/041) · D5 edge language (rec: Rust if within ~10–15%, decided by G4/HVPN-P1-004) · D6 asymmetric per‑leg transport (rec: defer to Phase 2; MVP is single‑transport hub‑and‑spoke) · D7 MVP ambition (rec: lean tunnel‑first MVP, this WBS) [SYNTHESIS §3].

## Sources

[04_P1] HelixVPN-Phase1-MVP.md — control‑plane modular monolith, DDL+RLS, the Coordinator protobuf + WatchNetworkMap, Redis‑Streams event taxonomy, policy compiler, enrollment/PKI, helixvpnctl + quadlets, the §11.2 8‑criterion DoD + §11.3 SLOs + §11.4 no‑log lint (the spine of this WBS). · [04_P0] HelixVPN-Phase0-Spike.md — G1–G6 entry gates, the Transport trait, boringtun wrapper, MASQUE/CONNECT‑UDP, iOS memory harness, Go‑vs‑Rust edge, flutter_rust_bridge FFI, netns+DPI+netem rig. · [04_ARCH] HelixVPN-Architecture-Refined.md — control/data separation, ULA /48 + 4via6 (D4), no‑logging, default‑deny, repo layout. · [02] 02-control-plane.md — authoritative DDL, RLS, IPAM, protobuf, events, coordinator, API, deploy manifests (this WBS references, never re‑defines). · [01] 01-data-plane.md, [03] 03-client-core-and-ui.md, [04] 04-security-privacy-pki.md, [00] 00-product-scope-and-principles.md. · [05_YBO] Go+Gin+PG+Redis+Podman mandate. · [SYNTHESIS] §§1–9 — stack floor, the D1–D7 key decisions, ecosystem wiring (containers/helix_qa/challenges/docs_chain/security/vision_engine), constitution bindings (§11.4.27/.40/.58/.76/.85/.93/.106/.107/.113/.132/.151/.156/.159/.161/.162/.163/.169).