# Phase 2 (Parity + Reach) Subtask Deepening — epic → task → subtask (closes R5)

# Phase 2 (Parity + Reach) Subtask Deepening — epic → task → subtask (closes R5)

Revision: 2 Last modified: 2026-07-04T12:00:00Z Rev 2: Independent gap-analysis pass — structure and id-convention verified consistent with subtask-deepening-p1.md and 08-phase2-parity-wbs.md. No contradictions found.

Volume 7 (Phase Execution), document 4 of 5. Companion to subtask-deepening-p1.md, applying the same R5 deepening (REFINEMENT_NOTES.md) to Phase 2: every task HVPN-P2-NNN in 08-phase2-parity-wbs.md is decomposed into PR-sized subtasks HVPN-P2-NNN.k (§11.4.93/.54), each with a concrete acceptance (falsifiable, captured-evidence §11.4.5/.69/.107), the §11.4.169 test types (the 08-… §1 vocabulary, now including DDOS — re-armed for the public multi-region surface), and an estimated complexity (XS/S/M/L, sizing-only TARGET, §11.4.6). Spec-only. Phase 2's load-bearing premise — everything is additive (08-… §0) — means most subtasks are "more impls of an existing seam", and two epics (E21 DAITA, E24 PQ) carry the measure-don't-assert privacy-claim discipline (self-validated analyzers, §11.4.107(10)). Every subtask traces to its parent task in 08-…; nothing is invented beyond decomposing stated work. These .k rows feed the workable-items DB (workable-items-model.md §7).

## Table of contents

- 0. Deepening conventions

- 1. E19 — Phase-1 seam certification (entry)

- 2. E20 — Full transport / obfuscation set

- 3. E21 — DAITA traffic-analysis defense

- 4. E22 — Direct P2P + NAT traversal + relay

- 5. E23 — Multi-hop (nested WireGuard)

- 6. E24 — Post-quantum handshake (ML-KEM PSK)

- 7. E25 — Desktop apps (Windows, macOS)

- 8. E26 — Policy-as-code & GitOps

- 9. E27 — HA + multi-region fleet

- 10. E28 — Observability additions

- 11. E29 — QA · SLOs · DoD certification

- 12. E30 — Governance & release

- 13. Subtask roll-up + measure-don't-assert note

- Sources verified

## 0. Deepening conventions

Identical to subtask-deepening-p1.md §0: id (HVPN-P2-NNN.k) · Subtask (≥6 words §11.4.91) · Acceptance (falsifiable, captured-evidence) · Tests (§11.4.169 codes, 08-… §1 vocabulary incl. DDOS) · Cx (XS/S/M/L sizing TARGET). A subtask is complete only with a test_diary evidence path (workable-items-model.md §9). Two anti-bluff escalations specific to Phase 2 (08-… §0): (a) any "direct path" claim is Direct only when a non-gateway src is observed at the peer (§11.4.107 — no false direct); (b) DAITA + PQ privacy claims MUST be measured with a self-validated analyzer (golden-bad fixture must FAIL the analyzer), never asserted. Complexity sums to ≈ parent effort (08-… §19, ~259 person-days excl. entry seams) — sizing only, never a date.

## 1. E19 — Phase-1 seam certification (entry)

Entry gate (not Phase-2 work; tracks that the reserved seams exist, 08-… §5).

HVPN-P2-190 — Transport-trait seam present (XS) · 191 — Peer.endpoint candidate-list seam (XS) · 192 — federated Coordinator + PKI hooks (XS). Each is a single seam-audit subtask:

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| 190.1 | Register a no-op stub transport + walk the ladder unchanged | the ladder walks the stub with zero changes to the trait | UNIT,INT | XS |
| 191.1 | Audit NetworkMap.Peer.endpoint is a repeated EndpointCandidate | the field is repeated; a coordinator delta can populate it | UNIT | XS |
| 192.1 | Audit coordinator statelessness + a PKI PSK-injection hook | coordinator hydrates from store+events; PKI exposes a PSK hook | UNIT,SEC | XS |

## 2. E20 — Full transport / obfuscation set

Every new transport is just another impl of the unchanged Phase-1 Transport trait.

HVPN-P2-200 — Shadowsocks-wrap transport (08-… §6; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Wrap WG datagrams in a Shadowsocks AEAD stream (reuse shadowsocks-rust primitives) | tunnel survives udp drop+quic drop nft rules (E2E) | UNIT,INT,E2E | M |
| .2 | DPI-gauntlet classifier check | tshark sees no WG/QUIC signature (SEC) | SEC,CHAL | S |
| .3 | Goodput record with TCP-HoL caveat | goodput captured + HoL noted (BENCH) | BENCH | S |

HVPN-P2-201 — UDP-over-TCP (UoT) transport (08-… §6; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Length-prefix WG over a single TCP conn; ladder ranks last | tunnel comes up under udp drop (all ports); reachability preserved (E2E) | UNIT,E2E | S |
| .2 | HoL penalty measured + documented | HoL overhead captured (BENCH) | BENCH | XS |

HVPN-P2-202 — LWO hardening (per-session keyed header obfuscation) (08-… §6; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Per-session-keyed obfuscation of WG header signature bytes + randomized padding | a WG-signature DPI rule that drops plain-WG fails to classify LWO-v2 (SEC) | UNIT,SEC,CHAL | M |
| .2 | Overhead < 2% vs plain-UDP | captured overhead < 2% (BENCH) | BENCH | XS |

HVPN-P2-203 — Refined auto-escalation ladder + per-network memory (08-… §6; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Ladder FSM with per-step failure budget (N handshakes/T seconds) | client converges to shadowsocks on a UDP+QUIC-blocked network (E2E) | UNIT,E2E | M |
| .2 | network_memory per SSID/gateway fingerprint | on the next connect to the same network, escalation latency is skipped (captured timing delta) | FA,CHAL | M |

HVPN-P2-204 — Coordinator-pushed regional priors (08-… §6; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | TransportPolicy.region_prior map in NetworkMap; region-keyed reorder | a censored-region-resolved client gets a reordered ladder + connects on the prior's head transport | UNIT,INT,E2E | S |

HVPN-P2-205 — Aggregate censorship-evasion telemetry (08-… §6; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Record aggregate "transport X after N escalations in region R" (no per-user data) + Grafana panel | dashboard renders transport-mix by region | UNIT,CHAL | S |
| .2 | No-log schema-lint mutation: a per-user evasion table FAILs | the planted per-user table FAILs the build (SEC) | SEC | XS |

HVPN-P2-206 — Hysteria2/Salamander interop evaluation (D1/D6) (08-… §6; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | A/B benchmark Hysteria2+Salamander vs MASQUE/H3 (goodput under loss, DPI evasion parity) | recorded §20 decision-log row + CSV; rec: keep MASQUE primary, Hysteria2 optional rung | BENCH,E2E | S |

## 3. E21 — DAITA traffic-analysis defense

Adopt maybenot (the engine behind Mullvad DAITA) — do not roll your own.

HVPN-P2-210 — maybenot engine integration (08-… §7; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Embed maybenot::Framework as a shaping stage (on_packet pad, tick cover) over WG datagrams | outgoing datagrams pad to uniform sizes; cover packets emit on schedule (capture: size histogram collapses) | UNIT,INT | M |
| .2 | Machines-as-config (data, not code) loading | a known padding machine loads + drives shaping | UNIT,BENCH | S |

HVPN-P2-211 — Machines-as-data distribution via NetworkMap (08-… §7; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | NetworkMap.daita field carrying signed maybenot machine defs | a coordinator-pushed machine update changes shaping live (no rebuild) | UNIT,INT,E2E | S |
| .2 | Signature-verify machine blobs before load | a tampered blob is rejected (captured) | SEC,INT | S |

HVPN-P2-212 — DAITA opt-in toggle + honest cost surface (08-… §7; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | DaitaToggle widget (off by default) + Riverpod binding + live cover_ratio readout | UX MP4 shows toggling DAITA, the cost note, the live overhead (§11.4.159 vision-verified) | UI,UX,REC | S |

HVPN-P2-213 — Closed-world fingerprinting efficacy harness (the privacy claim) (08-… §7; L)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Closed-world WF classifier trained on captured traces; DAITA-off vs DAITA-on | DAITA-on accuracy < DAITA-off by the documented margin on the project's own fixtures | FA,SEC,BENCH | L |
| .2 | Self-validated analyzer (golden-good reduces accuracy; golden-bad no-op machine does NOT, §11.4.107(10)) | the golden-bad no-op machine FAILs the analyzer (proves no-bluff) | CHAL,SEC | M |
| .3 | Cover-traffic overhead recorded | overhead captured + surfaced honestly | BENCH | S |

## 4. E22 — Direct P2P + NAT traversal + relay

The gateway becomes a coordinator + relay-of-last-resort; traffic goes direct where NAT allows.

HVPN-P2-220 — STUN-like endpoint discovery (08-… §8; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Host + server-reflexive candidate discovery via the gateway STUN endpoint → ReportStatus | a node behind NAT reports a correct server-reflexive ip:port (INT) | UNIT,INT,E2E | M |
| .2 | STUN endpoint refuses amplification (response ≤ request, rate-limited) | flood test: no amplification, rate-limit holds (DDOS) | DDOS | S |

HVPN-P2-221 — Candidate distribution via WatchNetworkMap (08-… §8; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Reuse WatchNetworkMap as the signaling channel: push each peer the other's candidates as a Peer.endpoint delta | both peers receive candidates within the SLO1 budget (captured) | UNIT,INT,E2E | S |
| .2 | Candidates policy-filtered (need-to-know) | an unauthorized peer never appears in candidates (SEC) | INT,SEC | S |

HVPN-P2-222 — UDP hole punching across the NAT-type matrix (08-… §8; L)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Simultaneous WG handshake probes to all candidates; WG roaming latches the working src | direct datagrams captured bypassing the gateway for full/restricted/port-restricted pairs | UNIT,E2E,STRESS | L |
| .2 | Symmetric-on-both-ends → clean relay fallback | symmetric pairs fall through to relay; no false "direct" claim (§11.4.107) | SEC,CHAL | M |

HVPN-P2-223 — helix-relay (DERP-style encrypted relay fallback) (08-… §8; L)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Edge relay mode keyed by destination pubkey (below the WG crypto boundary) | a symmetric-NAT pair communicates via relay (E2E) | UNIT,INT,E2E | L |
| .2 | Relay holds only ciphertext, no per-flow durable record; tenant/region-fungible | memory/pcap inspection proves only pubkey-keyed ciphertext (no plaintext) | SEC,STRESS | M |
| .3 | Relay forwarding throughput | captured forwarding BENCH | BENCH | S |

HVPN-P2-224 — Path selection: start-relay, upgrade-to-direct (08-… §8; M · SLO1)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Start on relay, attempt direct in background, upgrade seamlessly; report path | SLO1: direct-path establishment (non-symmetric NAT) > 90% within 10 s (histogram) | UNIT,E2E,PERF,FA | M |
| .2 | No connectivity gap on upgrade | relay is the instant fallback; no user-visible reconnect | FA | S |

HVPN-P2-225 — Continuous direct-path health-check + downgrade (08-… §8; S · SLO2)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Health-loop: relay→direct upgrade < 15 s, no reconnect; direct→relay downgrade on degradation | SLO2 < 15 s upgrade (captured); injected degradation downgrades within the window | UNIT,E2E,PERF,CHAOS | S |

HVPN-P2-226 — Path indicator UI + UX (08-… §8; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | PathIndicator bound to the core status stream | UX MP4 shows relay→direct on upgrade and direct→relay on injected degradation (§11.4.159) | UI,UX,REC | S |

## 5. E23 — Multi-hop (nested WireGuard)

Client → Entry → Exit so no single node sees both who you are and where you go.

HVPN-P2-230 — Hop-chain computation in the coordinator (08-… §9; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Compute the hop chain (respect exitNodes + user selection), per-hop keys, hops list in NetworkMap | Entry=EU/Exit=US yields a two-hop map with distinct per-hop keys (INT) | UNIT,INT | M |
| .2 | Enforce exitNodes policy | an unauthorized exit is never offered (SEC) | SEC | S |

HVPN-P2-231 — Nested-session construction in helix-core (08-… §9; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Build nested WG (outer Client↔Entry obfuscated, inner Client↔Exit plain) — transport/DAITA on outer only | end-to-end reachability through Entry→Exit (E2E) | UNIT,E2E | M |
| .2 | Second-hop overhead measured | goodput/latency overhead captured + documented | BENCH | S |

HVPN-P2-232 — Hop-isolation capture assertions (the privacy proof) (08-… §9; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Pcap at each hop: Entry sees client IP not dest; Exit sees dest not client IP | P2-AC4 both isolation invariants proven by pcap | SEC,E2E,CHAL | M |
| .2 | Mutation: collapse to single hop FAILs the assertion | the single-hop-collapse mutation FAILs | CHAL,SEC | S |

HVPN-P2-233 — Multi-hop picker UI (08-… §9; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | MultiHopPicker (region/jurisdiction labelled) bound to the policy-permitted hop set | UX MP4 shows selecting Entry/Exit + the two-hop connection with jurisdiction labels (§11.4.159) | UI,UX,REC | S |

## 6. E24 — Post-quantum handshake (ML-KEM PSK)

Close harvest-now-decrypt-later via a PQ-derived PSK mixed into WG — without forking WG crypto.

HVPN-P2-240 — ML-KEM PSK exchange over the control channel (08-… §10; L)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | ML-KEM (FIPS 203) exchange over the authenticated Coordinator RPC (no new listener) → HKDF → WG PSK | two PQ-capable peers establish a WG session whose PSK is ML-KEM-derived (captured) | UNIT,INT,SEC | L |
| .2 | PSK rotates on each rekey; exchange at setup/rekey only | PSK rotation captured; no per-packet KEM | SEC,BENCH | M |

HVPN-P2-241 — Hybrid combiner (never PQ-only) + capability negotiation (08-… §10; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | PSK = HKDF(classical ¦¦ pq) combiner + capability flags | PQ-capable↔classical-only pairs interoperate (negotiate down without error) | UNIT,SEC,E2E | M |
| .2 | Mutation: PQ-only combine FAILs | a PQ-only combine FAILs the unit + mutation gate | UNIT,SEC | S |

HVPN-P2-242 — Downgrade-safety guard (08-… §10; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Downgrade FSM: a PQ failure → classical-or-fail-closed, never weaker | injecting a PQ failure yields classical-or-fail-closed, never weaker-than-classical (captured) | SEC,E2E,CHAL | M |
| .2 | MITM strip-PQ detection logged as a control event | a strip-PQ attempt is detected/logged (not as traffic) | SEC | S |

HVPN-P2-243 — PQ default-on where supported + adoption metric (08-… §10; S · SLO5)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | PQ default-on for capable pairs + PqChip + helix_pq_sessions_ratio | SLO5: PQ adoption among capable pairs > 95% (dashboard) | UNIT,PERF,REC | S |
| .2 | Zero steady-state per-packet cost | per-packet benchmark ≈ 0 delta vs classical | PERF | S |

HVPN-P2-244 — Rosenpass alternative evaluation (decision) (08-… §10; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Evaluate Rosenpass vs in-house ML-KEM (audit pedigree, integration cost) | recorded §20 decision row; rec: ship in-house ML-KEM, keep a Rosenpass KemSuite adapter | BENCH,SEC | S |

## 7. E25 — Desktop apps (Windows, macOS)

Everything above the shim is the same helix-ui + helix-core.

HVPN-P2-250 — Windows privileged service + wireguard-nt shim (08-… §11; L)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Windows service hosting helix-core over wireguard-nt/wintun + named-pipe IPC | connect → reach an authorized LAN host from Windows; app unprivileged, service holds tunnel | INT,E2E,REC | L |
| .2 | Code-signed driver + service (Authenticode) | driver + service signature verified | SEC | M |

HVPN-P2-251 — macOS NEPacketTunnelProvider shim (08-… §11; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | macOS NE hosting helix-core (desktop memory budget), notarized + signed | connect → reach from macOS; notarization + signature verified; UX recording (§11.4.159) | INT,E2E,SEC,REC | M |

HVPN-P2-252 — Desktop split-tunnel (per-app routing) (08-… §11; L)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Windows WFP filters + macOS app-bound rules, include/exclude set from the shared UI | a designated app routes outside the tunnel while the rest stays inside (pcap proves the split per-app on both OSes) | UNIT,E2E,SEC | L |
| .2 | Split-tunnel UX recording | UX MP4 of the split-tunnel screen (§11.4.159) | UX,REC | S |

HVPN-P2-253 — Desktop kill-switch + DNS-leak parity (08-… §11; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | WFP (Win) + NE rules (mac) kill-switch wired to core state | on forced drop, host-side pcap shows zero plaintext + zero DNS leak on both OSes (§11.4.107) | SEC,E2E,REC | S |

## 8. E26 — Policy-as-code & GitOps

Git becomes the source of truth; the apply runner is the tenant's own runner (§11.4.156, no active server-side CI).

HVPN-P2-260 — helixvpnctl policy compile --dry-run effect-diff (08-… §12; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Render the compiled effect delta (which devices gain/lose which access) | a PR adding one ACL line produces a human-readable effect-diff naming the exact devices/targets | UNIT,INT | M |
| .2 | Mutation: a hidden granted edge FAILs the diff completeness check | the hidden-edge mutation FAILs | SEC,CHAL | S |

HVPN-P2-261 — GitOps apply runner + tenant-token auth (08-… §12; M · P2-AC7)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | On merge, tenant runner helixvpnctl policy apply (token-auth) → persist version → emit policy.compiled → converge | P2-AC7: a merged PR converges the fleet < 1 s (helix_reconcile_seconds p99) with the effect-diff reviewed | INT,E2E,FA | M |
| .2 | No secrets in the repo (declarative intent only; sops/age refs) | secret-leak audit green (§11.4.10) | SEC | S |

HVPN-P2-262 — GitOps round-trip safety (drift detect + rollback) (08-… §12; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | helixvpnctl policy diff/rollback; idempotent apply | an out-of-band change is flagged as drift; a revert PR restores the prior compiled state byte-identically (captured) | INT,CHAOS,SEC | S |

## 9. E27 — HA + multi-region fleet

Same images, only topology changes (08-… §13/§17).

HVPN-P2-270 — Stateless coordinator fleet + stream re-pin (08-… §13; L)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | N stateless coordinators per region; rebuildable cache from PG+NATS | coordinator holds no local durable state (§11.4.108 clean-restart) | UNIT,INT,SCALE | M |
| .2 | Stream re-pin: agent re-pins to a sibling, resumes from known_version | killing a coordinator mid-stream re-pins + resumes with zero missed deltas (captured) | CHAOS | M |

HVPN-P2-271 — Postgres HA (Patroni) + regional read replicas (08-… §13; L)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Single logical primary + sync replicas + Patroni auto-failover | killing the PG primary fails over with no committed-write loss (CHAOS) | INT,CHAOS,SCALE | L |
| .2 | Regional read replicas serving coordinator hydration; RLS/no-log on replicas | regional coordinators hydrate from local replicas; invariants hold (SEC) | SEC,SCALE | M |

HVPN-P2-272 — NATS JetStream cross-region event mesh (Redis swap) (08-… §13; L · SLO4)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | NatsJetStreamBus impl behind the unchanged EventBus interface (durable subjects = Phase-1 taxonomy 1:1) | the taxonomy is identical to Phase 1 (no event renamed) | UNIT,INT | M |
| .2 | Cross-region propagation p99 < 2 s | SLO4 cross-region p99 < 2 s (captured) | E2E,PERF,SCALE | M |
| .3 | Region partition + heal shows no event loss | durable subjects replay; no loss (CHAOS) | CHAOS | M |

HVPN-P2-273 — Edge/relay fleet + client steering (Anycast/GeoDNS + RTT list) (08-… §13; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Anycast + GeoDNS fallback; NetworkMap.gateways candidate list; client picks by RTT | a client picks the nearest edge by measured RTT; Anycast routes UDP/QUIC to the closest PoP | INT,E2E,PERF | M |
| .2 | STUN/edge handshake flood rate-limited | flood shed without dropping legit tunnels (DDOS) | DDOS | S |

HVPN-P2-274 — Regional failover flow + floating IPs (08-… §13; M · P2-AC8/SLO3)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Health prober → gateway.failover{from,to} → NetworkMap delta → client re-handshake; floating IPs | SLO3: gateway failover → client reconnected p99 < 3 s | E2E,CHAOS,PERF | M |
| .2 | Existing direct-P2P sessions unaffected by region loss | P2-AC8: region kill reconnects clients < 3 s, zero policy/identity loss, direct sessions survive (chaos capture) | CHAOS | M |

## 10. E28 — Observability additions

Counts + health only, never destinations/flows (08-… §14).

HVPN-P2-280 — Reach/evasion KPI dashboards (08-… §14; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Transport-mix/region, escalation depth, direct-vs-relay ratio, hole-punch success by NAT-type, PQ adoption %, DAITA overhead % (aggregate) | dashboards render every KPI from aggregate counters | INT,CHAL | M |
| .2 | No-log lint mutation: a per-flow source table FAILs | the per-flow mutation FAILs the no-log lint (§11.4 / §02 §2.4) | SEC | S |

HVPN-P2-281 — Multi-region health (NATS lag, PG replication, convergence p99) (08-… §14; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Per-region coordinator health + NATS consumer lag + PG replication lag + cross-region convergence-p99 panels + alerts | convergence-p99 panel reflects P2-SLO4 + alerts on breach; lag alerts fire under an injected partition (captured) | INT,PERF,SCALE | S |

## 11. E29 — QA · SLOs · DoD certification

Each surface is a measure-don't-assert gate; privacy/efficacy claims carry self-validated analyzers (§11.4.107(10)).

| Parent task | Subtask focus (.1/.2) | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| 290 NAT-traversal matrix | .1 full/restricted/port-restricted/symmetric harness | every theoretically-direct pair achieves direct (pcap bypass); symmetric relays cleanly; no false direct | E2E,STRESS,FA,CHAL | L |
| 291 obfuscation gauntlet | .1 each transport through its DPI block + tshark classifier | P2-AC1: each transport survives its block + the classifier confirms the disguise | E2E,SEC,CHAL | M |
| 292 DAITA efficacy cert | .1 accuracy-drop with the self-validated analyzer wired into meta-test | P2-AC2: DAITA-on accuracy drops materially; golden-bad no-op FAILs the analyzer; cost surfaced | FA,SEC,CHAL | M |
| 293 PQ interop + downgrade cert | .1 classical↔PQ negotiation + downgrade safety | P2-AC5: all capability pairs interoperate; every injected PQ failure → classical-or-fail-closed (captured) | SEC,E2E,CHAL | M |
| 294 multi-hop isolation cert | .1 per-hop pcap assertions | P2-AC4: both isolation invariants proven; single-hop-collapse mutation FAILs | SEC,E2E,CHAL | S |
| 295 HA/chaos cert | .1 kill coordinator/PG primary/region | P2-AC8 + SLO3 (failover p99<3s) + SLO4 (cross-region p99<2s) green; no control-plane data loss; direct sessions survive | CHAOS,SCALE,PERF,FA | L |
| 296 DDoS resilience cert | .1 STUN + edge handshake flood | STUN response ≤ request (no amplification); edge sheds a flood without dropping legit tunnels below SLO | DDOS,SEC,STRESS | M |
| 297 Phase-2 DoD cert + discovery sweep | .1 full-suite retest + enumerated discovery (§11.4.118) | all 8 P2-AC + 5 P2-SLO green with evidence; the discovery set surfaces zero release-blockers (else §11.4.129) | FA,CHAL,REC | M |

## 12. E30 — Governance & release

HVPN-P2-300 — Phase-2 items DB projection + docs-chain sync (08-… §16; M)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Project the Phase-2 leaves into docs/workable_items.db via the reused Phase-1 loader + .docs_chain/contexts/wbs-p2.yaml | md↔db byte-identical round-trip (§11.4.93); a leaf edit re-syncs exports; verify is the gate | UNIT,INT,FA | M |

HVPN-P2-301 — Phase-2 release tagging + multi-upstream publish (08-… §16; S)

| id | Subtask | Acceptance | Tests | Cx |
| --- | --- | --- | --- | --- |
| .1 | Cut <HELIX_RELEASE_PREFIX>-2.0.0-parity (§11.4.151) on main + every owned submodule; publish via merge-onto-latest-main (no force-push §11.4.113) | git tag -l '<PREFIX>-2.*' enumerates the whole release; HVPN-P2-297 cert is the tag's evidence; reachable on every remote | FA | S |

## 13. Subtask roll-up + measure-don't-assert note

| Epic | Parent tasks | Deepened subtasks | Risk note |
| --- | --- | --- | --- |
| E19 entry seams | 3 | 3 | prereq audits |
| E20 transport set | 7 | 15 | additive impls of one trait |
| E21 DAITA | 4 | 8 | measure-don't-assert |
| E22 P2P/NAT | 7 | 14 | no-false-direct (§11.4.107) |
| E23 multi-hop | 4 | 7 | isolation proven by pcap |
| E24 PQ | 5 | 9 | never-weaker-than-classical |
| E25 desktop | 4 | 6 | per-app split-tunnel |
| E26 GitOps | 3 | 5 | effect-diff completeness |
| E27 HA/multi-region | 5 | 11 | failover SLOs |
| E28 observability | 2 | 4 | aggregate-only, no-log holds |
| E29 QA/DoD | 8 | 8 | self-validated analyzers |
| E30 governance | 2 | 2 | items-DB + tag |
| Total | 54 | 92 | — |

The two privacy-claim epics (E21 DAITA, E24 PQ) and the NAT-traversal epic (E22) carry the load-bearing anti-bluff escalations (08-… §0/§19): a green pass that asserts a privacy claim without the measurement is a §11.4 PASS-bluff; a "direct" path claimed without a non-gateway src observed at the peer is the same class. Every subtask's acceptance is a captured-evidence assertion (§11.4.5/.69/.107); the golden-bad fixture FAILing the analyzer is the proof the harness cannot bluff (§11.4.107(10)). Complexity sums to ≈ 08-… §19's ~259 person-days — sizing only, never a date (§11.4.6).

## Sources verified

- 08-phase2-parity-wbs.md §5–§16 (every task Desc/Deliverable/Acceptance/Effort/Tests), §17 HA topology, §18 traceability, §19 critical path, §20 open decisions — read 2026-06-26.

- Sibling workable-items-model.md (§3/§6/§9), dependency-graph.md (§5 Phase-2 DAG), subtask-deepening-p1.md (§0 conventions) — authored this volume.

- Constitution anchors §11.4.5/.6/.10/.40/.54/.58/.69/.85/.91/.93/.107/.108/.113/.118/.129/.132/.151/.156/.159/.169 — read 2026-06-26.

Honest boundary (§11.4.6): subtasks decompose stated Phase-2 work. DAITA/PQ efficacy subtasks are measure-don't-assert — their acceptance is a measured delta with a self-validated analyzer, never an asserted claim. Complexity is sizing TARGET only; DDOS subtasks are now applicable (public multi-region surface), the Phase-1 NOT_APPLICABLE deferral re-armed.